[image: image31.png]&y
I 1700reRR



[image: image32.png]4
”ITALFERR



[image: image33.png]4
”ITALFERR



[image: image34.png]4
”ITALFERR



[image: image35.png]4
”ITALFERR



 

[image: image36.png]4
”ITALFERR



[image: image37.png]4
”ITALFERR




Report cover page

	Project Title:
	Review of Railway Rehabilitation in Central Asia

	Project Number:
	65290 – EuropeAid/116151/C/SV/Multi

	Countries:
	Kazakhstan, Kyrgyzstan, Tajikistan and Uzbekistan

	
	Local operators
	EC Consultant

	Name:
	Republican State Enterprise 

“KAZAKHSTAN TEMIR ZHOLY” 

Mr. Talaspekov K.S.
	State Company

“KYRGYZ TEMIR ZHOLU”

 Mr. Isaev K. Sh. 


	ITALFERR S.p.A.

	Address:
	98, Pobeda av., 473000, Astana, Kazakhstan
	83, L. Tolstoy str., 720009, Bishkek, Kyrgyz Republic
	via Marsala, 53/67 – 00185 

Rome – Italy

Akhunbabaeva ul, 15 – 700047

Tashkent – Uzbekistan

	Tel:
	(3172)935002
	(998312) 657068
	+39.06.49752721

+998.71.1321237

	Fax:
	(3172) 935836
	(996312) 651441
	+39.06.49752209

+998.71.1321286

	Name:
	Tajik Railways

 Mr. Khukumov A.
	State Joint Stock Railway Company

“UZBEKISTON TEMIR YULLARI”

Mr. Ramatov A. J.
	E-mail:

a.veralli@italferr.it
italferr@litel.uz

	Address:
	35, Nazarshoev str., 734012 Dushanbe, Tajikistan
	7, T.Shevchenko str., 700060 Tashkent, Uzbekistan
	

	Tel:
	(992372) 216059
	(99871) 1388414
	

	Fax:
	(992372) 218334
	(99871) 1320552
	

	
	

	Contact Person:
	Project Director
Alessandro Veralli
	Team Leader
Paul Pezant

	Signature:
	 __________________________
	 __________________________

	
	


Date of report:

31 July 2005
Authors of report:

Project Team

	EC M & E team
	(name(
	(signature(
	(date(

	NCU Kyrgyzstan
	(name(
	(signature(
	(date(

	TACIS Bureau

(task manager(
	(name(
	(signature(
	(date(


ABBREVIATIONS

ABLS

Automatic Block Line System

ADB

Asian Development Bank

ALC

Automatic Level Crossing

BC

Border crossing

CAR

Central Asian Republic

COTIF

Convention concerning the International Transport of Goods by Rail

CIS

Commonwealth of Independent States

CTC

Central Traffic Control

CWR

Continuous Welded Rail

EAEC

Euro Asian Economic Community

EBRD

European Bank for Reconstruction and Development

EC

European Commission 

ECE

UN Economic Commission for Europe

ECO

Economic Cooperation Organisation

ECMT

European Council of Ministers of Transport

EDD

Unified Transit Tariff

EIRR

Economic Internal Rate of Return

ERII

Electric Relay Interlocking Installation

EU

European Union

FSU

Former Soviet Union

GDP

Gross Domestic Product

IGC

Intergovermental Commission TRACECA 

IMF

International Monetary Fund

IRU

International Road Transport Union

IsDB

Islamic Development Bank

JBIC

Japanese Bank for International Cooperation

KAZ

Kazakhstan

KGZ

Kyrgyz Republic

KTZ

Kazakhstan Temir Zholy (Kazakhstan national railways)

MLA

Multilateral Agreement on International Transport for Development of TRACECA 

KZT

Kazakhstan Tenge

LC

Level Crossing

MKDII

Mechanic Key dependent Interlocking Installation

MOTC

Ministry of Transport and Communications

MTT

International Railway Tariff

OECD

Organisation of Economic Co-operation and Development

OSJD

Organisation for the Cooperation in Railways (based in Varshaw)

PRC

People’s Republic of China

PW

Permanent Way (rails, sleepers, fastenings, ballast)

SIS

Static Interlocking System

SMGS

Agreement on International Railway Freight Transport

SPECA
Special Programme for the Economies in Central Asia

TA

Technical Assistance

TACIS

Technical Assistance for the Commonwealth of Independent States

TAJ

Tajikistan

TAR

Trans-Asian Railway

TEU

Twenty Foot Equivalent Unit

TIR

Transport International Routier

TOR

Terms of Reference

TRACECA
Transport Corridor Europe Caucasus Asia

UIC

Union International des Chemins of Fer (based in Paris)

UN

United Nations

UNDP

United Nations Development Programme

UNESCAP
United Nations Economic and Social Commission for Asia and the Pacific

USAID

United States Agency for International Development

USD

United States Dollar

UTY

Uzbek Temir Yullari (Uzbekistan national railways)

UZB

Uzbekistan

WTO

World Trade Organisation
TABLE OF CONTENTS

iExecutive summary

0.
Project synopsis
5
1.
Introduction
8
2.
Description of the present situation
11
2.1
Permanent Way and earthworks
11
2.2
Stations
36
2.3
Level Crossings
37
2.4
Geology of the line
38
2.5
Structures and Drainages
39
2.6
Avalanche shed
43
2.7
Ballast quarry
45
3.
Description of the designed improvements
48
3.1
Methodology for the line construction (Permanent Way)
51
3.1.1
Methodology 1
51
3.1.2
Methodology 2
54
3.2
Methodology for rail welding
58
3.2.1
Thermic welding
59
3.2.2
Electric Flash-butt Welding
61
3.2.3
Formation of Continuous Welded Rails (CWR)
62
3.3
Methodology for beam substitution and rehabilitation of bridges
63
3.4
Construction of a new avalanche shed
68
4.
Purchase of machines (Lot 3.1)
69
4.1
Description and bill of quantity
69
4.2
Costs estimates
69
5.
Purchase of permanent way materials (Lot 3.2)
70
5.1
Description and bill of quantity
70
5.2
Costs estimates
71
6.
Purchase of a sleeper factory (Lot 3.3)
72
6.1
Description
72
6.2
Cost estimate
72
7.
Detailed Design of Civil works (Lot 3.4)
74
7.1
Description and bill of quantities
74
7.2
Costs estimates
75
7.2.1
Unit costs
75
7.2.2
Cost calculation flow
76
8.
Implementation schedule
79
9.
Tender Documents
83
9.1
Introduction
83
9.2
The adopted philosophy for procurement
83
10.
Conclusions
87


Appendix 1 – Tolerance for rail welding

ANNEXES

Annex A:
Lot 3.1 – Purchase of machines
Annex B:
Lot 3.2 – Purchase of permanent way materials

Annex C:
Lot 3.3 – Purchase of a sleeper factory

Annex D: 
Lot 3.4 – Civil works

Executive summary

After the development of the Feasibility Study (March 2005), project activities aimed at producing tender documents suitable for international tender for rehabilitation measures for the Kazakh Border – Bishkek – Balikchi railway line. The present document is to report the conclusions of such activities of Detailed Design and Tender Documents.

Historically the section under study belongs to the line Lugovaya – Bishkek – Balykchi as it is shown in the following Fig. 1 – 1.

Figure - The Lugovaya – Bishkek – Balykchi railway line

[image: image38.png]4
”ITALFERR



[image: image1.jpg]



After the collapse of the former Soviet Union, the line has been split into two sections because of the introduction of the national border between Kyrgyzstan and Kazakhstan: the Lugovaya - border (61 km) and the border – Bishkek – Balykchi (322 km).

The administrative change could not change so much the situation since the two sections are still working in conjunction. Furthermore services along the line are operated up to Lugovaya by the Kyrgyz Railways and so they will be up to 2007 at least. This is why the report is making reference to the whole line.

Besides this fact, improvements along the section from Balykchi to the border should be certainly managed by the Kyrgyz Railway Administration while the section up to Lugovaya belongs to the Kazakh Railways but maintenance/services are operated by the Kyrgyz Railways. Consequently the issue of the competence has required to consider two different Feasibility Studies for rehabilitation measures concerning sections of the same line.

The development of activities for the Detailed Design and Tender Documents preparation has started from the feasibility study delivered in March 2005. 

In the following meetings with Kyrgyz Railways representative, the proposed solution was discussed and some changes have been requested and introduced in the Detailed Design as for instance: the reduction of the length of the avalanche shed to be built, the purchase of a welding machine, the rehabilitation of 5 bridges, the rehabilitation of the quarry for the ballast located nearby the station of Djil Aryk.

The proposed option represents the low cost alternative, mainly consisting in provision of PW materials, machines and plants that would permit to face the most urgent necessities of the line, as well as in building the indispensable structures to guarantee the line protection from land-slides. 

The option considers in particular the following rehabilitation works:

a. Civil works concerning earthworks;

b. Permanent way replacing works

c. Existing permanent way rail welding and tension regulation;

d. Re-alignment, leveling and ballast cleaning on the existing sections;

e. Civil works concerning structures (basically bridges and avalanche shed);

The adopted option by the Feasibility Study considers that all activities (but major civil works like for the bridges and for the avalanche shed) will be basically carried out by the Kyrgyz Railways personnel during a sort of extraordinary maintenance which will be possible after purchasing materials, machines and plants.

Therefore four Lots have been considered for international tendering:

· Lot 3.1 – Purchase of machines

· Lot 3.2 – Purchase of Permanent Way materials

· Lot 3.3 – Purchase of a sleeper factory

· Lot 3.4 – Civil works

Lot 3.4 also includes the rehabilitation of the ballast quarry near Djil Aryk in order to reach a proper level of efficiency and increase the production needed for the rehabilitation of the railway track.

Lots 3.1 and 3.2 regard the purchase of those materials and machines which are needed for the rehabilitation works carried out directly by the Kyrgyz Railways. Lot 3.3 is for purchase of a sleeper factory and Lot 3.4 regards civil works (bridges, avalanche shed and quarry rehabilitation) both will be performed by a Contractor under a Design-Build and Turnkey contract.

Costs for each Lot have been estimated to be:

· Lot 3.1 – 8.4 millions US$

· Lot 3.2 – 10.8 millions US$

· Lot 3.3 – 2.0 millions US$

· Lot 3.4 – 7.9 millions US$

International standard Tender Documents for each Lot have been prepared by the Consultant to assure International Competitive Bidding.

For Lot 3.1 and Lot 3.2, the ADB Standard Tender Documents (STD) for Procurement of Goods have been taken as reference while for Lot 3.3 and Lot 3.4, the ADB Standard Bidding Documents (SBD) for Design-Build and Turnkey have been taken as reference.

In the case of Procurement of Goods the following steps have been considered:

A - prequalification of bidders, and

B - tender for procurement of goods (single stage)

In the case of the Design-Build and Turnkey tender the following steps have been included:

A - prequalification of bidders, and

B - design-build and turnkey tender (single stage)

In all cases the tenders should be lunched using international standards but the work performed, leaves open the possibility of adopting guidelines of procurement of other bodies. Thus the approach doesn’t prevent the Beneficiary to implement the project using other guidelines (i.e. World Bank, EBRD, national, etc.) simply taking the core part of the tender document, namely the technical drawings and specifications, and embedding them into a different set of standards documents.

The Consultant has presented such documents in separate Annexes (Annex A, B, C and D) which can be straight used for the tender just including some basic additional information from the Beneficiary (i.e. employer’s name and address, representative of the employer, deadline for presentation, etc).

It is worth mentioning that the subdivision of the rehabilitation works in four lots involving smaller amounts of money can favour the releasing of a loan or of a grant. The last is certainly desirable due to the importance of the Kazakh Border – Bishkek – Balykchi railway line for the whole country and taking into account Kyrgyz railways financial performance.

0. Project synopsis

	Project Title:
	Review of Railway Rehabilitation in Central Asia

	Project Number:
	65290 – EuropeAid/116151/C/SV/Multi

	Country:
	Kazakhstan, Kyrgyz Republic, Tajikistan, Uzbekistan


Wider project objectives: 
The development of viable, secure, safe and competitive transport routes linking the countries of Central Asia with Europe and other neighbouring countries. Strengthened border management capacity facilitating economic development, the movement of people and goods and the prevention of organised crime.


The object of the project is to carry out:


Module A / Analysis of the relevant national railway transport plans and any regional railway transport planning provisions.


Module B / Preparation of Technical and Economic Justifications to support and to attract the investments for the rehabilitation of railway lines in the Kyrgyz Republic, Kazakhstan and Uzbekistan for the purpose of increasing transportation capacities of these areas. Preparation of Feasibility study of measures for the maintenance, rehabilitation and renewal of the freight wagon fleet of the Tajik Railways.

Specific project objectives:

The project will carry out:

Module A /

· Overview of relevant traffic flows and forecasts, with special attention on freight transport from Central Asia towards Europe especially through TRACECA corridor;
· Identification of weaknesses and bottlenecks;
· Investigation on the cross-border elements, including co-operation in exchange of data and in customs (also with Afghanistan);
· Evaluation of multi-modal dimensions and possibilities for inter-operability;

· Harmonisation of standards and of operating procedures, with particular attention to compatibility with EU standards, in particular with regard to safety and security standards for the transportation of dangerous goods and oil products.

Module B /

Technical and Economic Feasibility Studies for the rehabilitation and construction of new railways lines. Pursuant to the Technical and Economic Justification data there will be prepared the loan applications to the lending banks for the allocation of investments to implement the projects. 

Feasibility Study of measures for the maintenance, rehabilitation and renewal of the freight wagon fleet of the Tajik Railways.

Planned outputs:
Module A /
· Recommendations concerning multimodal transport

· Recommendations on harmonisation of standards and operating procedures and interoperability.

· Recommendations on improvements of border-crossing procedures.

· Traffic forecasts.

· Tentative prioritisation of recommended actions. 


Module B /
· Technical and economic feasibility study of the railway line sections previously identified in Kazakhstan, Kyrgyzstan and Uzbekistan.

· Draft tender document for the same sections.

· Definition of a policy for the maintenance, rehabilitation and renewal of wagons in Tajikistan.

· Feasibility study and preparation of tender documents for rehabilitation and renewal of the existing workshops and maintenance plants in Tajikistan.

Project activities:
Module A /
A.1 – Collection and review of transport and economic studies. Data collection

A.2 – Overview of traffic flows

A.3 – Identification and review of physical, geopolitical, social and environmental issues 

A.4 – Analysis of national railway transport plans and regional railway transport planning provisions.

A.5 – Traffic forecasts – Identification of capacity bottlenecks

A.6 – Investigation of border-crossing issues – Recommendations for improvement at borders

A.7 –Review of multimodal transport – Identification of development bottlenecks – Recommendations for improved services

A.8 – Harmonisation of standards and of operating procedures – Recommendations on standards adaptation and improved inter-operability

A.9 – Selection of railway section to be submitted to feasibility study under Module B

A.10 – Discussion with the Project Partners representatives

A.11 – Refining output of Module A 


Module B /
Activities to be developed in Kazakhstan, Kyrgyzstan and Uzbekistan:

B.1 - Traffic Analysis

B.2 - Technical Feasibility

B.3 - Environmental Impact

B.4 - Economic Viability

B.5 - Detailed Design

B.6 - Rehabilitation/construction implementation schedule

B.7 - Draft tender documents preparation

Activities to be carried out in Tajikistan:

B.8 - Feasibility Study of measures for maintenance, rehabilitation and renewal of the freight wagon fleet of the Tajik Railways

Project starting date:
1 March 2004

Project duration:
18 months

1. Introduction

The present document is to report the conclusions of the activities of Detailed Design and Tender Documents developed following the Feasibility Study of the rehabilitation measures for the Kazakh border – Bishkek – Balykchi railway section in Kyrgyzstan delivered in March 2005.

Historically the section under study belongs to the line Lugovaya – Bishkek – Balykchi as it is shown in the following Fig. 1 – 1.

Fig 1 – 1- The Lugovaya – Bishkek – Balykchi railway line

[image: image39.png]4
”ITALFERR



[image: image2.jpg]



After the collapse of the former Soviet Union, the line has been split into two sections because of the introduction of the national border between Kyrgyzstan and Kazakhstan: the Lugovaya - border (61 km) and the border – Bishkek – Balykchi (322 km).

The administrative change could not change so much the situation since the two sections are still working in conjunction. Furthermore services along the line are operated up to Lugovaya by the Kyrgyz Railways and so they will be up to 2007 at least. This is why the report is making reference to the whole line.

Besides this fact, improvements along the section from Balykchi to the border should be certainly managed by the Kyrgyz Railway Administration while the section up to Lugovaya belongs to the Kazakhstan Railways but maintenance/services are operated by the Kyrgyz Railways. Consequently the issue of the competence has required to consider two different Feasibility Studies for rehabilitation measures concerning sections of the same line.

Since it is the only railway connection in the north of the country and the more important in the whole country, the line is of strategic importance for Kyrgyzstan and for its economy. 

Additional to that, Kyrgyzstan has not a railway linking northern cities (i.e. Bishkek) with the southern ones (i.e. Osh, Jal Alabad) and actually transport demand uses either road or the railway Balykchi – Bishkek - Lugovaya and then up to the south crossing Kazakhstan, Uzbekistan and also Tajikistan.

Improvements are consequently required for the line not to act as a bottleneck for the economic activities, to give access to the international markets and to connect Bishkek with the regional market.

The development of activities for the Detailed Design and Tender Documents preparation has started from the feasibility study delivered in March 2005. After that date, meetings have been held with the highest representatives of the Kyrgyz railways to discuss details of the option proposed in the Feasibility Study (“Option 1”).

Comments have been positive and Kyrgyz Railways representative showed interest in the proposed solution, which has to consider due to the severe financial constraints of the Kyrgyz railways. Some changes have been requested and introduced in the Detailed Design as for instance: the reduction of the length of the avalanche shed to be built, the purchase of a welding machine, the rehabilitation of 5 bridges, the rehabilitation of the quarry for the ballast located nearby the station of Djil Aryk.

The proposed option represents the low cost alternative, mainly consisting in provision of PW materials, machines and plants that would permit to face the most urgent necessities of the line, as well as in building the indispensable structures to guarantee the line protection from land-slides. It would allow the acceleration of the capital maintenance of the remaining network putting at disposal recovered rails and machines to implement works with Kyrgyz railways personnel.

The Consultant has consequently undertaken the Detailed Design and the Tender Documents preparation for the best option selected during the Feasibility Study and agreed with Kyrgyz Railways.

The option considers in particular the categories in which the whole rehabilitation works can be divided to be:

a. Civil works concerning earthworks;

b. Permanent way replacing works

c. Existing permanent way rail welding and tension regulation;

d. Re-alignment, leveling and ballast cleaning on the existing sections;

e. Civil works concerning structures (basically bridges and avalanche shed);

The activities concerning civil works (bridges and avalanche shed) are to be developed by a Contractor on the basis of a design and build contract.

All other works will be performed directly by the Kyrgyz Railways using internal personnel following the purchase of materials, machines and plants.

Therefore four lots have been considered:

· Lot 3.1 – Purchase of machines

· Lot 3.2 – Purchase of Permanent Way materials

· Lot 3.3 – Purchase of a sleeper factory

· Lot 3.4 – Civil works.

Lot 3.4 also includes the rehabilitation of the ballast quarry near Djil Aryk in order to reach a proper level of efficiency and increase the ballast production needed for the rehabilitation of the railway track.

In all cases the tender should be an international tender, but for Lot 3.3 and Lot 3.4 a Design-build and Turnkey (Single Stage) tender has been adopted while for Lot 3.1 and Lot 3.2 a Procurement of Goods Tender should be adopted.

In both cases the Consultant has developed tender documents packages using international standards (ADB standards). In the case of the Design-build and Turnkey tender the following steps have been included:

A - prequalification of bidders, and

B - design-build and turnkey tender (single stage)

In the case of “procurement of goods” the following steps have been considered:

A - prequalification of bidders, and

B - tender for procurement of goods (single stage)

Such approach of using international standards, leaves open the possibility of adopting guidelines of procurement of bodies other than ADB. Thus the approach doesn’t prevent the Beneficiary to implement the project using other guidelines (i.e. World Bank, EBRD, national, etc.) simply taking the core part of the tender document, namely the technical drawings and specifications, and embedding them into a different set of standards documents.

The Consultant has presented such documents in separate Annexes (Annex A, B, C and D) which can be straight used for the tender just including some basic additional information from the Beneficiary (i.e. employer’s name and address, representative of the employer, deadline for presentation, etc).

Finally, despite the positive results, it has to be pointed out that the project has been largely affected by the national Kyrgyz law covering “classified information”.

As already explained, this heritage of the former Soviet Union prevents the access to a large series of information to foreign people including those geographically referred such as detailed maps, locations of stations/bridges/structures and including train timetable, traffic details, etc.

It has to be noted that such constraints could have also counterproductive effects vis-à-vis design standards required by IFIs for releasing a loan. Thus other projects could be preferred just for being better presented: for instance such constraint didn’t allow the Consultant to produce plans and profiles and has required a working methodology more numerical/analytical, so less intuitive.

Notwithstanding Kyrgyz Railways have always been observant of the rules, they have been also very constructive in supporting experts staff both in the site visits and in the technical discussion.

It is worth mentioning that the subdivision of the rehabilitation works in four lots involving smaller amounts of money can favour the releasing of a loan or of a grant. The last is certainly desirable due to the importance of the Kazakh Border – Bishkek – Balykchi railway line for the whole country and taking into account Kyrgyz railways financial performance.

2. Description of the present situation

2.1 Permanent Way and earthworks

In the mid XIX when the only type of transport between Central Asia and Kazakh steppes were horses and camels, caravan and mail roads were in condition of full decline. This circumstances and as well as the issues of strengthening military-political and economic influence of Russia in Central Asia, the possibility of wide use of rich sources of row materials and sales market in the South-East of Russian empire, striving for direct exit from these regions to Siberia, stimulated the emergence in 1878 of the project on connection of Central Asia and Syberia.

The Turksib (Turkestan – Siberia) railway line was at last implemented during 1913-1931, creating conditions for wider development of cotton-growing in Central Asia Republics and providing them with grain from Siberia.

Construction and development of railways in Kyrgyz Republic was implemented by stages. Lugovaya – Pispek (Bishkek 1) was put into operation in 1924, according to the project of construction of Turksib line. Due to some unclear reasons, the project was then changed and the construction of railways was carried on according to the economic possibilities, necessities and needs: Pishpek – Frunze (Bishkek 2) in 1929, Frunze – Kant in 1932 to connect a sugar refinery, Kant – Tokmak in 1941, Tokmak – Bystrovka in 1942, Bystrovka – Ribachye (Balykchi) in 1950.

After the collapse of former Soviet Union (1991), the Lugovaya – Kazakh border section, in spite of being in Kazakh republic territory, continue up till now to be maintained and operated by Kyrgyz railways. Meetings were held recently between Kazakh and Kyrgyz governments to agree the passage of this section to the operation and maintenance of Kazakh railways.

As the Consultant collected information about a probable passage of this line to Kazakh railways within the 2007, Lugovaya – Kyrgyz border and Kazakh border – Bishkek – Balykchi were considered separately. 

The description of the existing Kazakh border-Balykchi line section can be done in the frame of the definitions established in line with the former Soviet railway rules (which for instance has been substantially absorbed by Uzbek Railways by the order 70”H” dated 09.11.95), concerning types and elements of permanent way, track works, maintenance and periodicity of their execution. In fact, even if the line under study for geographic and administrative reasons is located in Kyrgyzstan, it has been assumed by this Consultant that such rationale could be applied in terms of line classification and therefore of simulation of the future needs for line maintenance, according to the classification that will be recovered after the rehabilitation works.

From the following tables 2.1 – 1 and 2.1 - 2 the line classification in categories, by their technical characteristics, and in groups, by density of freight traffic, is possible.

Table 2.1 – 1 - Track classification.

	[image: image40.png]4
”ITALFERR



Track group
	Density of freight traffic, mln. tkm gross weight km/per year
	Track category

	
	
	1
	2
	3
	4
	5
	6
	7

	
	
	Speed: passenger trains is numerator;

freight trains is denominator, km/h
	Station, branch and other tracks

	
	
	121-140

> 80
	101-120

> 70
	81-100

> 60
	61-80

> 50
	41-60

> 40
	40 and less
	

	
	
	
	
	
	
	
	main reception/departure tracks
	

	
	
	Main tracks
	
	

	А
	> 80
	1
	1
	1
	2
	2
	3
	5 class

	B
	50-80
	1
	1
	2
	2
	3
	3
	

	C
	25-50
	1
	2
	2
	3
	3
	4
	

	[image: image41.png]4
”ITALFERR



D
	10-25
	1
	2
	3
	3
	4
	4
	

	E
	10 and less
	2
	2
	3
	3
	4
	4
	


Considering that the section under study had in the last years a freight traffic of 1,0÷1,5*106/year gross tons, and that, on almost all the section, the speed is for the time being 70-50 km/h and that old wooden sleepers and worn out P50 rails are installed on the major part of the section, it is possible to conclude that this line is currently classified as an E4 line.

This classification will be used in the next Chapters and paragraphs. 

Table 2.1 - 2 Technical terms and conditions for track laying and maintenance according to its class
	Track class

	1
	2
	3
	4
	5

	1. Superstructure constructions

Continuous welded rail (CWR) tracks on reinforced concrete sleepers or link track on timber sleepers

	2. Types and characteristics of superstructure

	New temperature –resistant R65 rails, 1 group, 1 class; new fastenings; new sleepers (impregnated timber, 1 group). Sleepers profile: on direct lines and curves R>1200 m - 1840 pcs/km; on curves with R<1200 m and less - 2000 pcs/km. Ballast: gravel or asbestos with the layer depth of 35 cm under timber sleepers ; 40 cm – under reinforced concrete sleepers.


	New R65 rails or used ones in accordance with the Table 2.3.

 New or repaired used fastenings and sleepers – in accordance with Technical Conditions for the usage of used superstructure materials. Profile and the group of rails are the same as on the 1st and 2nd class tracks. 

Gravel or asbestos ballast, with layer depth of 25 cm under timber rails and 30 cm under reinforced concrete sleepers.
	Used R65 rails – in accordance with the Technical Conditions for the usage of used superstructure rails. Used fastenings and sleepers, as a rule repaired ones. 

Sleeper profile is the same as on the 1 - 3 class rails. The laying of new sleepers of 2nd group is allowed. 

Ballast: gravel, asbestos, gravel and sand with layer depth of 20 cm under timber sleepers and 25 cm under reinforced concrete ones. 
	Rails, fastenings and sleepers are all used ones of all types, including the ones unusable in track laying of the 3rd and 4th class but not lighter than R 43.

Interlacing of used reinforced concrete sleepers with timber ones is allowed. 

Sleepers profile: 1440 pcs/km on direct lines; 1600 pcs/km on curves with R< 650 m.

Ballast depth underneath the sleeper not less than 15 cm. 


Alignment and gradients

The total length of Kazakh border – Balykchi section is 261,403 km.

The alignment is mostly on straight from Kazakh border up to Bishkek 1 (5,2 km of curves out of 90 km in length), from Bishkek 1 to Balykchi the number of curves greatly increases as well as the slopes especially in the last part of the section up to a total of 44,4 km out of 172 km in length. Every circular curve is provided with parabolic transition curves at the beginning and at the end. 

· The minimum curve radius is 260 m. 

· The maximum cantilever is 150 mm.

· The maximum gradient is 20 %o, at chainage km 3892 between Djil Aryk and P 148.

· The maximum allowed load is 23 t/axle

The Tab. 2.1 – 3, shown in the following pages, contains all the relevant data about the line:

· curves and their characteristics (length, deviation angle, radius, cant),

· level crossings location,

· stations with start, end and centre (building) chainage. The chainage is referred to the first and last turnouts blades.

Tab. 2.1 - 3
1/6

	Element
	Start
	End
	Station centre
	Cant
	Deviation angle
	Radius
	Curve
	Transition

	 
	(km)
	(km)
	(km)
	(cm)
	(degree)
	-60
	(m)
	length
	length

	 
	 
	 
	 
	 
	 
	 
	 
	(m)
	(m)

	Kazakh border
	3685.746
	3686.816
	3686.324
	 
	 
	 
	 
	 
	 

	L.C.
	3686.956
	
	
	
	
	
	
	
	 

	Curve
	3688.654
	3689.036
	
	7
	20
	8
	800
	381
	100

	Curve
	3689.161
	3689.522
	
	6
	18
	42
	800
	361
	100

	L.C.
	3690.142
	
	
	
	
	
	
	
	 

	L.C.
	3691.960
	
	
	
	
	
	
	
	 

	Curve
	3692.371
	3692.712
	
	5
	11
	44
	1000
	341
	40

	Curve
	3693.075
	3693.485
	
	6
	25
	3
	800
	409
	60

	Curve
	3693.799
	3694.066
	
	6
	13
	20
	900
	269
	60

	Curve
	3697.569
	3697.606
	
	4
	1
	40
	2000
	146
	20

	 
	3697.606
	3697.792
	
	2
	0
	37
	3600
	96
	20

	L.C.
	3698.967
	
	
	
	
	
	
	
	 

	L.C.
	3702.417
	
	
	
	
	
	
	
	 

	Kaindi
	3702.578
	3703.838
	3703.322
	 
	 
	 
	 
	 
	 

	Curve
	3705.268
	3705.467
	
	11
	8
	51
	900
	159
	40

	L.C.
	3705.425
	
	
	
	
	
	
	
	 

	Curve
	3705.803
	3706.038
	
	4
	4
	56
	2500
	236
	20

	L.C.
	3712.066
	
	
	
	
	
	
	
	 

	Curve
	3715.164
	3715.555
	
	0
	9
	42
	2200
	391
	20

	L.C.
	3715.900
	
	
	
	
	
	
	
	 

	Curve
	3716.133
	3716.354
	
	3
	5
	10
	2000
	220
	40

	L.C.
	3717.088
	
	
	
	
	
	
	
	 

	Curve
	3717.420
	3717.662
	
	4
	6
	23
	2000
	242
	20

	Kara-Balta
	3717.960
	3719.116
	3718.242
	 
	 
	 
	 
	 
	 

	L.C.
	3720.169
	
	
	
	
	
	
	
	 

	L.C.
	3722.456
	
	
	
	
	
	
	
	 

	L.C.
	3724.100
	
	
	
	
	
	
	
	 

	L.C.
	3726.617
	
	
	
	
	
	
	
	 

	R-141
	3730.419
	3731.506
	3730.908
	
	
	
	
	
	 

	Curve
	3733.122
	3733.401
	
	5
	12
	24
	1100
	278
	40

	L.C.
	3733.964
	
	
	
	
	
	
	
	 

	L.C.
	3737.029
	
	
	
	
	
	
	
	 

	Curve
	3738.638
	3739.063
	
	10
	32
	41
	640
	425
	60

	Belovodskaja
	3739.682
	3741.042
	3740.092
	 
	 
	 
	 
	 
	 

	L.C.
	3739.861
	
	
	
	
	
	
	
	 

	L.C.
	3741.943
	
	
	
	
	
	
	
	 

	Curve
	3742.393
	3742.588
	
	5
	5
	0
	2000
	194
	20

	Curve
	3745.184
	3745.463
	
	5
	13
	55
	900
	278
	60

	L.C.
	3747.418
	
	
	
	
	
	
	
	 

	Curve
	3753.382
	3753.527
	
	5
	4
	24
	1500
	145
	30

	Shopokovo
	3754.716
	3755.787
	3755.435
	 
	 
	 
	 
	 
	 

	L.C.
	3756.079
	
	
	
	
	
	
	
	 

	L.C.
	3761.310
	
	
	
	
	
	
	
	 

	Soklukh
	3764.750
	3765.850
	3765.212
	 
	 
	 
	 
	 
	 

	L.C.
	3769.560
	
	
	
	
	
	
	
	 

	L.C.
	3771.950
	
	
	
	
	
	
	
	 

	Bishkek - I
	3773.267
	3776.248
	3775.591
	 
	 
	 
	 
	 
	 


2/6

	Element
	Start
	End
	Station centre
	Cant
	Deviation angle
	Radius
	Curve
	Transition

	 
	(km)
	(km)
	(km)
	(cm)
	(degree)
	-60
	(m)
	length
	length

	 
	 
	 
	 
	 
	 
	 
	 
	(m)
	(m)

	Curve
	3775.124
	3775.183
	
	0
	1
	35
	500
	66
	40

	Curve
	3775.183
	3775.341
	
	2
	4
	28
	1200
	49
	20

	L.C.
	3777.041
	
	
	
	
	
	
	
	 

	Curve
	3777.260
	3777.490
	
	0
	16
	4
	600
	228
	60

	L.C.
	3778.094
	
	
	
	
	
	
	
	 

	Curve
	3779.022
	3779.326
	
	6
	10
	42
	1200
	303
	80

	L.C.
	3779.461
	
	
	
	
	
	
	
	 

	Bishkek - II
	3779.558
	3780.635
	3780.062
	 
	 
	 
	 
	 
	 

	Curve
	3780.784
	3781.226
	
	5
	20
	45
	1000
	442
	20

	Curve
	3781.873
	3782.184
	
	5
	10
	3
	1200
	250
	40

	Curve
	3783.057
	3783.341
	
	5
	7
	31
	1100
	244
	100

	Alamedin
	3783.550
	3784.654
	3783.915
	 
	 
	 
	 
	 
	 

	Curve
	3784.856
	3785.032
	
	3
	3
	43
	1900
	186
	60

	L.C.
	3787.064
	
	
	
	
	
	
	
	 

	Curve
	3788.722
	3788.938
	
	3
	5
	36
	1000
	215
	20

	Curve
	3790.738
	3791.195
	
	5
	19
	55
	1200
	458
	40

	L.C.
	3791.261
	
	
	
	
	
	
	
	 

	Curve
	3792.716
	3793.086
	
	5
	16
	54
	1000
	370
	40

	Curve
	3793.477
	3793.693
	
	5
	11
	9
	800
	236
	60

	Curve
	3798.208
	3798.809
	
	3
	15
	29
	2150
	601
	20

	L.C.
	3799.215
	
	
	
	
	
	
	
	 

	Kant
	3799.945
	3801.114
	3800.569
	 
	 
	 
	 
	 
	 

	L.C.
	3801.224
	
	
	
	
	
	
	
	 

	Curve
	3803.003
	3803.597
	
	4
	21
	10
	1500
	594
	40

	L.C.
	3804.717
	
	
	
	
	
	
	
	 

	Curve
	3804.720
	3804.958
	
	3
	5
	40
	2000
	238
	40

	Curve
	3805.479
	3805.872
	
	7
	32
	15
	600
	393
	60

	Curve
	3805.872
	3806.260
	
	9
	24
	4
	600
	372
	120

	Curve
	3806.444
	3806.602
	
	2
	3
	43
	1500
	157
	60

	Curve
	3806.623
	3806.740
	
	3
	3
	58
	1400
	117
	20

	Curve
	3806.878
	3806.986
	
	1
	3
	38
	1400
	109
	20

	Curve
	3807.022
	3807.162
	
	4
	3
	38
	1900
	140
	20

	L.C.
	3807.295
	
	
	
	
	
	
	
	 

	L.C.
	3812.417
	
	
	
	
	
	
	
	 

	Curve
	3816.950
	3817.221
	
	4
	7
	10
	2000
	270
	20

	Ivanovka
	3818.528
	3819.435
	3819.090
	 
	 
	 
	 
	 
	 

	L.C.
	3819.522
	
	
	
	
	
	
	
	 

	Curve
	3819.512
	3819.693
	
	9
	13
	14
	700
	182
	40

	Curve
	3819.693
	3819.793
	
	9
	9
	10
	500
	99
	40

	Curve
	3819.819
	3820.230
	
	11
	29
	34
	600
	411
	100

	Curve
	3820.426
	3821.003
	
	10
	49
	20
	600
	577
	60

	Curve
	3821.118
	3821.904
	
	10
	53
	18
	600
	786
	80

	Curve
	3821.924
	3822.462
	
	9
	43
	47
	600
	538
	80

	Curve
	3823.115
	3823.774
	
	7
	43
	15
	750
	659
	40

	Curve
	3823.788
	3824.114
	
	9
	21
	32
	600
	325
	100

	L.C.
	3826.695
	
	
	
	
	
	
	
	 

	Curve
	3830.631
	3831.298
	 
	3
	18
	17
	2030
	667
	120


3/6

	Element
	Start
	End
	Station centre
	Cant
	Deviation angle
	Radius
	Curve
	Transition

	 
	(km)
	(km)
	(km)
	(cm)
	(degree)
	-60
	(m)
	length
	length

	 
	 
	 
	 
	 
	 
	 
	 
	(m)
	(m)

	L.C.
	3832.903
	
	
	
	
	
	
	
	 

	Curve
	3834.580
	3834.963
	
	6
	8
	60
	1800
	382
	100

	Curve
	3835.838
	3836.140
	
	5
	7
	53
	1900
	301
	40

	L.C.
	3836.792
	
	
	
	
	
	
	
	 

	L.C.
	3838.447
	
	
	
	
	
	
	
	 

	Tokmak
	3839.124
	3840.326
	3839.568
	 
	 
	 
	 
	 
	 

	Curve
	3840.875
	3841.731
	
	4
	21
	40
	2000
	856
	100

	L.C.
	3841.151
	
	
	
	
	
	
	
	 

	L.C.
	3844.947
	
	
	
	
	
	
	
	 

	L.C.
	3848.263
	
	
	
	
	
	
	
	 

	L.C.
	3852.476
	
	
	
	
	
	
	
	 

	Curve
	3856.257
	3856.666
	
	9
	27
	29
	600
	408
	120

	L.C.
	3857.771
	
	
	
	
	
	
	
	 

	Curve
	3857.907
	3858.279
	
	8
	24
	15
	600
	372
	120

	L.C.
	3864.543
	
	
	
	
	
	
	
	 

	L.C.
	3868.028
	
	
	
	
	
	
	
	 

	Curve
	3870.010
	3870.685
	
	9
	58
	37
	600
	674
	60

	Bystrovka
	3870.789
	3871.960
	3871.521
	 
	 
	 
	 
	 
	 

	L.C.
	3872.189
	
	
	
	
	
	
	
	 

	Curve
	3872.065
	3873.272
	
	8
	103
	48
	600
	1207
	120

	Curve
	3873.307
	3873.649
	
	9
	23
	3
	600
	341
	100

	Curve
	3876.122
	3876.447
	
	10
	25
	30
	640
	325
	40

	L.C.
	3876.830
	
	
	
	
	
	
	
	 

	Curve
	3878.332
	3878.510
	
	3
	4
	58
	1600
	178
	40

	Curve
	3880.460
	3880.787
	
	4
	8
	40
	1900
	327
	40

	Djil-Aryk
	3883.592
	3884.624
	3884.336
	 
	 
	 
	 
	 
	 

	L.C.
	3884.634
	
	
	
	
	
	
	
	 

	Curve
	3884.637
	3884.934
	
	10
	48
	55
	300
	296
	40

	Curve
	3885.284
	3885.573
	
	6
	26
	14
	500
	288
	60

	Curve
	3885.694
	3885.870
	
	8
	22
	21
	400
	166
	40

	Curve
	3885.870
	3886.004
	
	8
	5
	27
	1200
	134
	40

	Curve
	3887.913
	3888.565
	
	6
	39
	25
	1000
	652
	80

	L.C.
	3888.891
	
	
	
	
	
	
	
	 

	Curve
	3890.620
	3891.013
	
	8
	27
	57
	600
	392
	100

	Curve
	3891.152
	3891.381
	
	8
	21
	21
	400
	229
	80

	Curve
	3891.432
	3891.571
	
	5
	9
	0
	600
	139
	60

	Curve
	3891.657
	3891.869
	
	6
	23
	55
	330
	212
	80

	Curve
	3891.872
	3892.156
	
	8
	38
	4
	320
	293
	80

	Curve
	3892.203
	3892.306
	
	1
	6
	0
	500
	103
	40

	Curve
	3892.441
	3892.576
	
	4
	14
	64
	400
	134
	40

	Curve
	3892.576
	3892.699
	
	4
	8
	26
	700
	123
	40

	L.C.
	3892.621
	
	
	
	
	
	
	
	 

	Curve
	3892.836
	3893.219
	 
	8
	33
	48
	800
	383
	100


4/6

	Element
	Start
	End
	Station centre
	Cant
	Deviation angle
	Radius
	Curve
	Transition

	 
	(km)
	(km)
	(km)
	(cm)
	(degree)
	-60
	(m)
	length
	length

	 
	 
	 
	 
	 
	 
	 
	 
	(m)
	(m)

	Curve
	3893.276
	3893.507
	
	9
	26
	51
	300
	270
	90

	Curve
	3893.513
	3893.716
	
	6
	13
	2
	500
	204
	90

	Curve
	3893.717
	3893.916
	
	8
	24
	58
	320
	199
	60

	Curve
	3894.001
	3894.224
	
	9
	26
	20
	900
	223
	90

	Curve
	3894.224
	3894.695
	
	9
	80
	22
	300
	471
	50

	Curve
	3894.751
	3895.065
	
	9
	37
	35
	309
	314
	120

	Curve
	3895.146
	3895.734
	
	6
	90
	27
	500
	588
	60

	Curve
	3895.649
	3895.829
	
	9
	20
	59
	300
	180
	70

	Curve
	3895.858
	3896.047
	
	5
	10
	26
	600
	189
	80

	Curve
	3896.109
	3896.344
	
	8
	34
	10
	300
	235
	80

	Curve
	3896.370
	3896.776
	
	10
	56
	8
	300
	406
	50

	Curve
	3896.809
	3897.138
	
	10
	45
	44
	300
	329
	90

	Curve
	3897.353
	3897.447
	
	1
	1
	56
	2200
	94
	20

	Curve
	3897.638
	3898.138
	
	4
	10
	1
	500
	500
	20

	Curve
	3897.776
	3898.037
	
	9
	44
	17
	300
	261
	30

	Curve
	3898.046
	3898.322
	
	6
	22
	35
	300
	276
	60

	Curve
	3898.274
	3898.428
	
	2
	7
	6
	1000
	154
	30

	Curve
	3898.696
	3898.851
	
	1
	13
	22
	450
	155
	60

	L.C.
	3898.928
	
	
	
	
	
	
	
	 

	Curve
	3899.031
	3899.114
	
	2
	6
	59
	800
	83
	20

	R-148
	3899.160
	3900.129
	3899.660
	 
	 
	 
	 
	 
	 

	Curve
	3899.582
	3899.920
	
	4
	22
	42
	600
	338
	100

	Curve
	3900.150
	3900.268
	
	2
	3
	52
	1600
	118
	20

	Curve
	3900.267
	3900.339
	
	1
	2
	44
	1300
	72
	20

	Curve
	3900.339
	3900.522
	
	2
	14
	53
	500
	180
	100

	Curve
	3900.522
	3900.712
	
	2
	7
	81
	1400
	190
	20

	Curve
	3900.767
	3900.882
	
	2
	12
	12
	400
	115
	30

	Curve
	3900.907
	3901.191
	
	10
	40
	56
	300
	284
	70

	Curve
	3901.280
	3901.613
	
	2
	22
	8
	500
	333
	140

	Curve
	3901.787
	3901.957
	
	6
	15
	50
	400
	170
	50

	Curve
	3902.240
	3902.555
	
	5
	22
	4
	610
	315
	80

	Curve
	3902.715
	3902.945
	
	8
	22
	52
	400
	230
	70

	Curve
	3902.950
	3903.178
	
	10
	32
	45
	400
	228
	70

	Curve
	3903.478
	3903.692
	
	4
	15
	21
	500
	214
	80

	Curve
	3903.723
	3903.933
	
	6
	14
	58
	500
	210
	80

	Curve
	3903.939
	3904.166
	
	8
	24
	0
	400
	227
	60

	Curve
	3904.170
	3904.391
	
	5
	20
	10
	400
	221
	80

	Curve
	3904.417
	3904.546
	
	6
	9
	82
	500
	129
	50

	Curve
	3904.765
	3905.009
	
	8
	33
	13
	300
	244
	70

	Curve
	3905.027
	3905.255
	
	8
	32
	5
	300
	228
	60

	Curve
	3905.255
	3905.434
	
	7
	19
	32
	350
	179
	50

	Curve
	3905.574
	3905.662
	
	2
	4
	1
	1050
	88
	30

	Curve
	3905.683
	3905.741
	 
	0
	4
	35
	600
	58
	21


5/6

	Element
	Start
	End
	Station centre
	Cant
	Deviation angle
	Radius
	Curve
	Transition

	 
	(km)
	(km)
	(km)
	(cm)
	(degree)
	-60
	(m)
	length
	length

	 
	 
	 
	 
	 
	 
	 
	 
	(m)
	(m)

	Curve
	3905.741
	3905.870
	
	8
	18
	15
	310
	129
	60

	Curve
	3905.891
	3906.165
	
	10
	45
	57
	300
	274
	60

	Curve
	3906.224
	3906.540
	
	10
	48
	55
	300
	316
	40

	Curve
	3906.600
	3906.841
	
	9
	34
	42
	300
	241
	60

	Curve
	3906.867
	3907.037
	
	6
	21
	6
	300
	170
	60

	Curve
	3907.067
	3907.227
	
	4
	19
	12
	300
	160
	60

	Curve
	3907.351
	3907.573
	
	7
	27
	10
	300
	222
	80

	Curve
	3907.606
	3907.791
	
	8
	20
	4
	300
	185
	80

	Curve
	3907.798
	3908.012
	
	6
	25
	39
	300
	214
	80

	Curve
	3908.148
	3908.446
	
	7
	42
	3
	300
	298
	60

	Curve
	3908.806
	3909.006
	
	7
	22
	51
	300
	200
	80

	Curve
	3909.030
	3909.174
	
	3
	12
	53
	400
	144
	80

	Curve
	3909.288
	3909.421
	
	2
	13
	21
	400
	133
	40

	Curve
	3909.425
	3909.537
	
	3
	10
	24
	400
	112
	40

	Curve
	3909.662
	3909.786
	
	3
	12
	6
	400
	124
	40

	Curve
	3910.125
	3910.258
	
	7
	17
	53
	300
	133
	40

	Curve
	3910.259
	3910.374
	
	6
	11
	2
	390
	115
	40

	Curve
	3910.400
	3910.519
	
	7
	12
	36
	360
	119
	40

	Curve
	3910.926
	3911.265
	
	3
	51
	28
	800
	339
	120

	Curve
	3912.200
	3912.398
	
	4
	15
	56
	500
	198
	50

	Curve
	3912.402
	3912.580
	
	9
	13
	9
	600
	178
	40

	Curve
	3912.628
	3913.135
	
	7
	53
	24
	400
	507
	120

	Curve
	3913.365
	3913.715
	
	8
	35
	51
	400
	350
	100

	Curve
	3913.737
	3914.041
	
	8
	32
	8
	400
	304
	80

	Curve
	3915.453
	3915.610
	
	1
	3
	22
	2000
	157
	40

	Curve
	3917.020
	3917.412
	
	7
	23
	49
	530
	392
	130

	Curve
	3917.715
	3918.265
	
	9
	11
	28
	450
	550
	80

	Curve
	3917.865
	3917.999
	
	10
	17
	42
	300
	134
	80

	Curve
	3918.018
	3918.219
	
	7
	20
	57
	330
	201
	80

	Curve
	3918.404
	3918.605
	
	7
	11
	10
	830
	201
	40

	Curve
	3918.693
	3919.021
	
	9
	45
	28
	360
	328
	80

	Curve
	3919.201
	3919.363
	
	8
	17
	33
	300
	162
	70

	Curve
	3919.640
	3920.025
	
	6
	25
	24
	600
	385
	120

	Curve
	3920.140
	3920.520
	
	10
	57
	29
	290
	380
	90

	Curve
	3920.520
	3920.821
	
	10
	43
	6
	320
	301
	60

	Curve
	3920.898
	3921.066
	
	6
	15
	27
	400
	168
	60

	Curve
	3921.151
	3921.350
	
	11
	23
	9
	370
	199
	100

	Curve
	3921.350
	3921.552
	
	9
	16
	56
	480
	202
	100

	Curve
	3921.686
	3922.043
	
	7
	24
	26
	650
	357
	80

	Curve
	3922.200
	3922.371
	
	1
	40
	19
	2000
	171
	20

	Curve
	3922.497
	3922.667
	
	6
	13
	57
	450
	170
	60

	Curve
	3922.734
	3923.257
	
	7
	58
	14
	460
	523
	40

	L.C.
	3925.116
	 
	 
	 
	 
	 
	 
	 
	 


6/6

	Element
	Start
	End
	Station centre
	Cant
	Deviation angle
	Radius
	Curve
	Transition

	 
	(km)
	(km)
	(km)
	(cm)
	(degree)
	-60
	(m)
	length
	length

	 
	 
	 
	 
	 
	 
	 
	 
	(m)
	(m)

	Curve
	3926.302
	3926.536
	
	3
	15
	52
	700
	234
	40

	Curve
	3926.678
	3926.889
	
	6
	18
	44
	400
	211
	80

	Curve
	3926.916
	3927.282
	
	8
	58
	30
	250
	366
	90

	Curve
	3927.484
	3927.600
	
	4
	3
	52
	1300
	116
	30

	Curve
	3927.600
	3927.738
	
	6
	8
	59
	500
	138
	60

	Curve
	3928.916
	3929.305
	
	6
	28
	35
	620
	389
	80

	Curve
	3929.759
	3930.351
	
	7
	58
	40
	500
	592
	60

	Curve
	3930.806
	3931.089
	
	17
	34
	58
	300
	283
	100

	Curve
	3931.136
	3931.337
	
	3
	9
	14
	1000
	204
	40

	Curve
	3931.464
	3931.839
	
	11
	54
	28
	300
	375
	80

	Curve
	3932.243
	3932.469
	
	6
	23
	50
	400
	226
	60

	Curve
	3932.716
	3932.968
	
	4
	10
	58
	900
	252
	80

	Curve
	3933.902
	3934.217
	
	8
	26
	35
	550
	315
	60

	Curve
	3934.583
	3934.787
	
	9
	25
	4
	260
	204
	90

	Curve
	3934.789
	3934.900
	
	3
	12
	20
	290
	112
	50

	Curve
	3934.900
	3935.068
	
	5
	10
	18
	600
	168
	60

	Curve
	3935.331
	3935.853
	
	4
	26
	29
	1000
	522
	60

	Curve
	3936.126
	3936.411
	
	5
	19
	35
	600
	285
	80

	Kojamat-Kurkol
	3936.746
	3937.509
	3936.941
	 
	 
	 
	 
	 
	 

	L.C.
	3938.255
	
	
	
	
	
	
	
	 

	Curve
	3938.272
	3938.583
	
	2
	8
	50
	1500
	311
	80

	Curve
	3941.959
	3942.399
	
	3
	12
	2
	2000
	440
	20

	L.C.
	3946.590
	
	
	
	
	
	
	
	 

	Curve
	3946.662
	3947.137
	
	5
	36
	48
	600
	475
	90

	Balykchi
	3947.175
	3948.683
	3947.757
	 
	 
	 
	 
	 
	 

	End point
	3954.300
	 
	 
	 
	 
	 
	 
	 
	 


Line formation 

The line formation from Kazakh border to Bishkek 1 and from Bishkek 1 up to the station of Djil Arik is constituted by embankments 1÷3 m height. From Djil Arik, situated at 800 m above sea level, the line climbs tortuously with a formation mainly in cut or semi cut along the Boomy canyon up to Balykchi, the last station, situated on the shore of the Issyk Kul lake at 1600 m above sea level.

The standard cross section of the formation is reported on Figures 2.1 – 1, 2 and 3 in which a slope of about 6% towards both sides, starting from a central strip 2,3 m wide, can be observed.

The top surface of the embankment width varies from 6,0 m to 7,1 m. 

Fig. 2.1 – 1


[image: image3.wmf]Axis of future

 II track.

Up to 12.0

6.0

    

Typical cross structure of embankment in height up to 12 m from clay soils, fine and powdery sand and it is easy weathered rock.

The note

: At erection of embankments from dry sand with a corner of a natural slope less than 340 their slopes are arranged more gentle slope .

0.02

1:1

1:1.5

Not more abruptly

0.02-0.04

Not less then 0.3

Reserve in width

< 10.0 m

1:1.75

0.02

1:1

1:1.5

0.02-0.04

Not more abruptly

Not less then 0.3

1:1.75

Reserve in width

< 10.0 m

7.0

4,1

1:1.5

0,15

2,3

1:1.5


Fig. 2.1 – 2

[image: image4.wmf]   Typical cross a profile of a ditch depth up to 12 m in loess-like soils and a loess, silty loams, fine and powdery sands, 

semi-rocky 

breeds and 

loam

s.

The note

: At height of a slope up to 2 m 

out of

 

ditch

's

 

shelfs are not arranged.

1:1.5

0,4

1:1.5

1,0

0.02

0,15

2,3

7,0

0,4

1:1.5

0,6

1:1.5

1:1.5

0.02

1,0

1:1.5

0,6


Fig. 2.1 – 3

[image: image5.wmf]1:1.5

0,4

1:1.5

0,6

0,15

2,3

7,0

1:1.5

1-0.5

0.02

1:1.5

0.02

0,6

1,0

1:1.5

   Typical cross section of a wide-cut formation


Superstructure

The typical superstructure cross-sections on straight track and on curve are shown in Fig. 2.1 – 4. On the top surface of the embankment is laid down a sandy gravel layer 0,2÷0,3 m thick, and a ballast layer 0,20÷0,35 m thick under sleepers.

Along the main line of the track section these are the technical characteristics:

· the sandy gravel layer and the ballast layer are, respectively, 0,2 and 0,3 m thick,

· both wooden and concrete sleepers are installed (see Fig. 2.1 – 5 and 2.1 – 6); they are laid down at a distance of 0,54 m / 0,50 m between their axels on straight / on curves of radius less than 1200 m (1840 / 2000 sleepers per km),

· P50 and P65 type of rails are laid down (see Fig. 2.1 – 7).

· fastenings rail-wooden sleepers and rail-reinforced concrete sleepers are shown in Fig. 2.1 – 8.

Fig. 2.1 – 4

[image: image6.wmf]1.09

1.09

0.6

0.15

0.59

0.58

0.16

5.82

5.52

2.3

1.01

4.32

0.60

The note:

h-s

ize of an eminence

 of an e

xterior rail in curves

b-s

ize of a broadening of a formation

c-

Size of a broadening of a ballast section

In brackets sizes are resulted at 

R<600m

1:1.5

0.35

1:1.5

Area = 1.5090

Perimeter = 11.6733

1:2

0.62+0.32h

(2.97) 2.87+2.67h

3.50+b

0.58(0.48)-2.67h+c

0.15

2.77-1.03h

3.50

2.17-0.91h

2.3

0.15

0.60+0.12h

(2.35) 2.25+2.35h

T

he macadam ballast 

h=0.30m

 under a sleeper

0.15

sandy gravel h=0.2m

0.2

1:2

i=1520/h

C

oefficient

Perimeter

=0.257

Area

=0.06425

Area = 1.6812

Perimeter = 13.0014

2.7

1:20

3.40 (3.50)

0.35 (0.45)

0.35

On curves track sections (sleepers ferroconcrete)

Types of a superstructure

On straight track sections (sleepers

 

ferroconcrete) at a formation width 7,0

m

Area = 0.2323

1:2

1:1.5

Area = 1.1061

Perimeter = 11.1945

Area = 1.6555

Perimeter = 12.382612

Area = 

1.88713744

1:1.5

0.35

T

he macadam ballast 

h=0.30m

 under a sleeper

0.15

sandy gravel h=0.2m

0.2

1:2

2.7

1:20

3.4

0.35

0.145

0.35

Area = 144.5691, Perimeter = 

139.2845


Fig. 2.1 –5


[image: image7.wmf]2750

2750

2750

2750

2750

2750

Types of timber sleepers:

а) Edging; б) not edging.

165

250

280

I B

180

160

150

230

260

230

260

II B

III B

150

160

150

160

180

150

425

b)

I A

250

II A

III A

105

130

230

230

Zone of check of width of sleeper bed

165

160

150

a)


Fig. 2.1 - 6


[image: image8.wmf]1:20

A-A

B-B

A-A

B-B

250

250

145

174

25

75

45

45

28

170

160

2700

300

170

1050

145

15

160

240

100

480

229

25

205

330

145

150

20

300

182

10

224

15

44xR1.5

75

28

44xR1.5

45

45

25

145

250

182

45

145

45

25

28xR2

28

75

250

2700

1050

75

28

45

25

45

145

250

174

28xR2

     

Design of ferroconcrete sleepers

a - such as C-73-1; b - such as C-73-2; c - cross sections and reinforcing of 

sleepers C-73-1; d - cross sections and reinforcing of sleepers such as C-73-2.

182

300

480

240

330

145

229

205

100

15

25

15

145

305

20

229

145

255

10

174

The appendix 

8

-

4


Fig. 2.1 – 7


[image: image9.wmf]0,08

2,25

0,78

2,54

R0,75

0

1,78

2,01

2,1

9

4,78

R4

1:20

1,8

2,3

2,53

2,66

3,06

9,6

5,37

6,6

0,53

446

O36

Cross profiles of standard rails

 (R75 R65 R50)

O36

O36

316

96

Facet 1,5 х 1,5 mm. Up to R 17 mm.

356

66

216

O34

O34

O34

Axis of the

bolt hole

R0,1

1,23

7,5

1,95

1,65

Neutral axis

Neutral axis

1,05

Line of the centres

1,96

Line of the centres

 

Axis of the bolt hole

2,33

1,93

3,53

1:4

4,15

R4

4,68

7,6

R1

1:4

1,35

y

0,8

x

0,07

1

2,29

0

3,6

2,1

R0,15

0,8

0,69

1:20

R0,75

y

R1,25

4,41

5,22

R 50

0,67

1,62

1:4

R0,2

1

x

0,77

0,97

R0,85

1:4

R0,35

96

316

446

O36

O36

O36

Facet 1,5 х 1,5 mm. Up to R 17 mm.

Axis of the

bolt hole

4,09

3,88

5,25

4,02

0,56

7,5

y

1,5

1:4

R0,2

2,23

1,13

R0,1

R1,25

R0,35

x

Neutral axis

Line of the centres

0,82

R0,75

1:4

1:20

0,98

R0,15

1

2,39

0,08

0,01

0,78

y

R 75

1

2,46

y

R 65


Fig. 2.1 – 8


[image: image10.wmf]1-

basic washer; 2-insulating bush; 

3,7-

coil-double

 spring collar; 

4-screw nut;

5-mortgage bolt; 6-the terminal 

clamp rigid; 8-clamp

 

bolt; 9-laying 

under abase of rail; 10-metal 

laying; 11-laying under the 

baseplate. 

Separate fastening

11

The mixed fastening with 

use of paddy spikes as 

the sheathe spikes

The mixed fastening

1- s

heathe spike

2- 

basic spike

1

2

1:20

The appendix 

8

-

6

5

4

3

2

1

7

4

8

9

10

1:20

6

1:20


Normally rails are provided in 25 m bars; so, when they are laid down, a joint has to be done every 25 m. To reduce the hammering at the passage of trains, the joints on one rail are displaced 3 cm from the relevant ones on the other rail along the track 

On lines equipped with concrete sleepers, a great reduction of hammering effect can be obtained by welding rails in long bars (continuous welded rails, cwr).

The great advantages of this technique, which will be described in the next paragraphs, are the increase in comfort for passengers and considerable reductions in noise, in wearing out of rails and rolling stocks, in costs of maintenance.

According to Russian standards the maximum length of welded rail bars in Central Asia countries is 900÷1000 m. At the beginning and at the end of the long welded bars a sequence of joints and short bars 12,5 m long has to be laid down to allow a limited ”expansion” of the long bar at the highest levels of temperature. The schemes to be implemented are reported on Fig. 2.1 – 9: 

Fig. 2.1 - 9
(measures in m)

[image: image11.emf] 

<600 m <300 m <300 m

12.5 m

3 joints

12.5 m

3 joints

>600 m >300 m >300 m

12.5 m

4 joints

12.5 m

4 joints

>300 m >300 m

12.5 m

4 joints

12.5 m

4 joints

Insulated joints

Insulated joints


The situation of the existing rails, sleepers, implementation of cwr on the section under study can be summarized as it follows (see Table 2.1 – 4).
Table 2.1 - 4
	Rehabilitation works for Lugovaya-Balykchi Line - Kazakh border-Balykchi section

	Permanent way and turnouts type 

	Stations
	 
	PW type

	 
	Name
	 
	Line and station main lines
	Stations turnouts

	 
	 
	start km
	end km
	 
	 
	 
	on main track

	 
	 
	 
	 
	Rail type 
	Sleepers
	Length 
	P65 1/11 
	P50 1/11

	N.
	 
	 
	 
	 
	 
	(m)
	(N.)
	(N.)

	 
	border
	0.000
	3687.280
	 
	 
	 
	 
	 

	 
	 
	3687.280
	3698.100
	P65
	W/C
	10820
	 
	 

	 
	 
	3698.100
	3702.578
	P65
	C
	4478
	 
	 

	1
	Kaindi
	3702.578
	3703.838
	P65
	W/C
	1093
	5
	 

	 
	 
	3703.838
	3717.960
	P65
	C
	14122
	 
	 

	2
	Kara-Balta
	3717.960
	3719.116
	P65
	W/C
	989
	5
	 

	 
	 
	3719.116
	3729.28
	P65
	W/C
	10164
	 
	 

	 
	 
	3729.280
	3730.419
	P50
	W/C
	1139
	 
	 

	3
	R-141
	3730.419
	3731.506
	P50
	W/C
	954
	4
	 

	 
	 
	3731.506
	3739.682
	P50
	W/C
	8176
	 
	 

	4
	Belovodskaja
	3739.682
	3741.042
	P65
	W/C
	1193
	5
	 

	 
	 
	3741.042
	3754.716
	P50
	W/C
	13674
	 
	 

	5
	Shopokovo
	3754.716
	3755.787
	P65
	W/C
	904
	5
	 

	 
	 
	3755.787
	3764.750
	P50
	W/C
	8963
	 
	 

	6
	Soklukh
	3764.750
	3765.850
	P50
	W/C
	967
	4
	 

	 
	 
	3765.850
	3773.267
	P50
	W/C
	7417
	 
	 

	7
	Bishkek - I
	3773.267
	3776.248
	P50
	W/C
	2447
	16
	 

	 
	 
	3776.248
	3779.558
	P50
	W/C
	3310
	 
	 

	8
	Bishkek - II
	3779.558
	3780.635
	P50
	W/C
	910
	2
	3

	 
	 
	3780.635
	3783.550
	P50
	W/C
	2915
	 
	 

	9
	Alamedin
	3783.550
	3784.654
	P50
	W/C
	904
	 
	6

	 
	 
	3784.654
	3799.945
	P50
	W/C
	15291
	 
	 

	10
	Kant
	3799.945
	3801.114
	P50
	W/C
	1002
	 
	5

	 
	 
	3801.114
	3818.528
	P50
	W/C
	17414
	 
	 

	11
	Ivanovka
	3818.528
	3819.435
	P50
	W/C
	774
	 
	4

	 
	 
	3819.435
	3839.124
	P50
	W/C
	19689
	 
	 

	12
	Tokmak
	3839.124
	3840.326
	P50
	W/C
	1035
	 
	5

	 
	 
	3840.326
	3870.789
	P50
	W/C
	30463
	 
	 

	13
	Bystrovka
	3870.789
	3871.960
	P50
	W/C
	1004
	 
	5

	 
	 
	3871.960
	3883.592
	P50
	W/C
	11632
	 
	 

	14
	Djil-Aryk
	3883.592
	3884.624
	P50
	W/C
	832
	 
	6

	 
	 
	3884.624
	3899.160
	P50
	W/C
	14536
	 
	 

	15
	R-148
	3899.160
	3900.129
	P50
	W/C
	869
	 
	3

	 
	 
	3900.129
	3922.080
	P50
	W/C
	21951
	 
	 

	 
	 
	3922.080
	3936.746
	P43
	W/C
	14666
	 
	 

	16
	Kojamat-Kurkol
	3936.746
	3937.509
	P43
	W/C
	696
	 
	2

	 
	 
	3937.509
	3947.175
	P43
	W/C
	9666
	 
	 

	17
	Balykchi
	3947.175
	3948.683
	P43
	W/C
	1341
	 
	5

	 
	 
	 
	 
	 
	 
	 
	46
	44


The following table resumes the permanent way type in stations (main track) and line.

Table 2.1 - 5
	PW type Kyrgyzstan

	
	Line
	Stations

	
	
	main track

	W/C+P65
	20,984 
	4,180 

	W+P43
	24,332 
	2,037 

	W/C+P50
	176,570 
	11,697 

	C+P65
	18,600 
	 


From the table could be observed that 

· 43,764 km of track - between the border and few km after Kara-Balta station, and in Belovodskaja and Shopokovo stations - are equipped with P65 rails, out of them 18,6 km are on reinforced concrete sleepers and in continuous welded rails (cwr), the remaining part is formed by jointed 25 m bars on mixed wooden/concrete sleepers,

· 188,267 km are equipped with P50 rails on mixed wooden/concrete sleepers,

· 26,369 km are equipped with P43 rails on mixed wooden/concrete sleepers.

All these measures do not consider turnouts length.

Stations PW

The station main lines are generally provided with P50 rails, with the exception of:

· Kaindi,

· Kara – Balta,

· Belovodskaja,

· Shopokovo.

The existing turnouts are P65 tg 1/11 type on the station main lines from the Kazakh border up to Bishkek 2, with the exception of this last station in which two P65 tg 1/11 and three P50 tg1/11 type turnouts are installed. From Alamedin to Balykchi the station main lines are all equipped with P50tg1/11 turnouts.

In total, on station main track the following turnouts are currently installed:

· 44 P65 tangent 1:11,

· 46 P50 tangent 1:11.

Visit of the line

The line was visited by Consultant’s experts in more then one occasion late in 2004 and in April/May 2005 from Kazakh border to Balykchi also by means of trolley put at their disposal.

In spite of the impossibility to obtain a number of “classified” documents, the railway officials were very collaborative and gave essential information that were needed for the present study.

PW defects of the line
During the site visit of the line the experts could check the present condition of the line and they could directly verify some information provided by the railway representatives. In detail, it has been noticed that:

· PW is old and worn out in many sections, rails type P50 and wooden sleepers are at their life limit, and their use leads to current heavy speed restrictions and to the sensitive risk of derailment for heavy trains (where the dynamic factor on the permanent way is higher);

· fastening devices, in particular those equipped on wooden sleepers, are old, and their fastening force is almost absent. Bolts and their parts are often worn out. Part of them is not properly working because of the conditions of the sleepers; old wooden sleepers are damaged and their retaining force on bolts and screw is low, 
· rail junctions (every 25m for the sections not interested by the C.W.R.) are old and worn out, many bolts are missing for vibration and hammering, 
· in correspondence with rail junction, hammering on the rails leaded to a rail consumption over the limits, in particular for those junction where the opening is larger than the maximum admitted, 
· general conditions of the alignment geometry have been lost and their preservation is very difficult because of the deformation of the track panels and the bearing capacity of the formation level;

· in parts of the line the lateral paths of 0,59 cm on both sides of the top embankment surface disappeared for the action of raining waters and blowing wind; consequently quantities of ballast fell down and were wasted;

· in many cases the shoulders of ballast on the sides of sleepers, that in normal conditions are 0,35÷0,45 m wide, are non-existent;

· most of the ballast is extremely polluted with clayey soil and sand, particularly in stations;

· generally there are not drainage ditches.

Maximum speeds along the section

Conditions of permanent way elements can cause the necessity to reduce the maximum allowed speed on the lines. Generally this measure is taken when:

· the head of rails is worn out up to the admissible values,

· the ballast layer is highly polluted,

· the sleepers are no more in reliable condition for mechanical wear, decay and cracking,

· turnouts are obsolete and their elements worn out (in particular blades and crossings),

· existing cross section is greatly reduced by wind or rain water erosion, 

· profile and alignment are far from the original designed ones,

· bridges and culverts needs interventions.

In the case of this section reductions of maximum speeds were imposed along all its length.

From the original 100 km/h speed for passenger trains and 90 km/h speed for freight trains, the maximum allowed speeds are, for the time being, the following:

Table 2.1 - 6
	Rehabilitation works for Lugovaya-Balykchi Line - Kazakh border-Balykchi section

	"without project" speed

	Chainage
	Section length
	Speed

	(km)
	(km)
	(km/h)

	3626
	 
	 

	 
	61
	70

	3687
	
	 

	 
	83
	70

	3770
	
	 

	 
	178
	50

	3948
	 
	 


For the original speed of the line, the Consultant has operated a detailed analysis based on the existing line geometrical value, aimed at calculating, per each curve and therefore per each section, the maximum admissible speed. 

The following table 2.1-7 shows the existing line geometrical maximum speeds, and the theoretical maximum speeds reached with the upgrading of some indicated curve cants (superelevation). Calculations have been carried out by taking into consideration the following values:

· maximum admissible value for “anc” (not compensated acceleration on curve)=0.55 m/sec2

· maximum admissible “anc” variation on the transition curves=0.20/0.15 m/sec3

These maximum speeds will be recovered with the proposed rehabilitation options.

Table 2.1 – 7 Existing and future curves parameters. Future speeds.

	Rehabilitation works for Lugovaya-Balykchi Line - Kazakh border-Balykchi section 1/4

	Existing and future line speed limits - curves modifications

	Existing situation
	"with project" situation

	Curves
	 
	 
	Existing cant 
	Existing R
	Max alignment speed
	Min length of transition curve
	Theoretical Max speed
	Cant to be increased
	Future cant value

	 
	 
	 
	(cm)
	(m)
	(km/h)
	(m)
	(km/h)
	 
	(cm)

	Curve
	3688.654
	3689.036
	7
	800
	100
	98.62
	100
	 
	 

	Curve
	3689.161
	3689.522
	6
	800
	95
	88.01
	100
	yes
	7

	Curve
	3692.371
	3692.712
	5
	1000
	105
	105.42
	100
	 
	 

	Curve
	3693.075
	3693.485
	6
	800
	95
	88.01
	100
	yes
	7

	Curve
	3693.799
	3694.066
	6
	900
	100
	90.21
	100
	 
	 

	Curve
	3697.569
	3697.606
	4
	2000
	140
	132.05
	110
	 
	 

	Curve
	3697.606
	3697.792
	2
	3600
	160
	126.01
	110
	 
	 

	Curve
	3705.268
	3705.467
	11
	900
	115
	96.92
	110
	 
	 

	Curve
	3705.803
	3706.038
	4
	2500
	150
	124.34
	110
	 
	 

	Curve
	3715.164
	3715.555
	0
	2200
	125
	126.86
	110
	 
	 

	Curve
	3716.133
	3716.354
	3
	2000
	135
	129.50
	110
	 
	 

	Curve
	3717.420
	3717.662
	4
	2000
	140
	132.05
	110
	 
	 

	Curve
	3733.122
	3733.401
	5
	1100
	110
	110.05
	110
	 
	 

	Curve
	3738.638
	3739.063
	10
	640
	95
	82.87
	110
	yes
	14

	Curve
	3742.393
	3742.588
	5
	2000
	140
	116.06
	110
	 
	 

	Curve
	3745.184
	3745.463
	5
	900
	100
	101.63
	110
	yes
	10

	Curve
	3753.382
	3753.527
	5
	1500
	125
	114.64
	110
	 
	 

	Curve
	3775.124
	3775.183
	0
	500
	60
	61.73
	90
	yes
	12

	Curve
	3775.183
	3775.341
	2
	1200
	100
	96.22
	90
	 
	 

	Curve
	3777.260
	3777.490
	0
	600
	65
	65.40
	90
	yes
	10

	Curve
	3779.022
	3779.326
	6
	1200
	115
	102.25
	90
	 
	 

	Bishkek - II
	3779.558
	3780.635
	 
	 
	 
	 
	90
	 
	 

	Curve
	3780.784
	3781.226
	5
	1000
	105
	105.42
	90
	 
	 

	Curve
	3781.873
	3782.184
	5
	1200
	115
	115.39
	90
	 
	 

	Curve
	3783.057
	3783.341
	5
	1100
	110
	110.05
	90
	 
	 

	Curve
	3784.856
	3785.032
	3
	1900
	130
	120.66
	110
	 
	 

	Curve
	3788.722
	3788.938
	3
	1000
	95
	89.94
	110
	yes
	7

	Curve
	3790.738
	3791.195
	5
	1200
	115
	115.39
	110
	 
	 

	Curve
	3792.716
	3793.086
	5
	1000
	105
	105.42
	110
	yes
	7

	Curve
	3793.477
	3793.693
	5
	800
	90
	78.79
	110
	yes
	10

	Curve
	3798.208
	3798.809
	3
	2150
	135
	117.24
	110
	 
	 

	Curve
	3803.003
	3803.597
	4
	1500
	120
	109.76
	90
	 
	 

	Curve
	3804.720
	3804.958
	3
	2000
	135
	129.50
	90
	 
	 

	Curve
	3805.479
	3805.872
	7
	600
	85
	78.26
	90
	yes
	10

	Curve
	3805.872
	3806.260
	9
	600
	90
	81.05
	90
	 
	 

	Curve
	3806.444
	3806.602
	2
	1500
	110
	101.65
	90
	 
	 


	Rehabilitation works for Lugovaya-Balykchi Line - Kazakh border-Balykchi section 2/4

	Existing and future line speed limits - curves modifications

	Existing situation
	"with project" situation

	Curves
	 
	 
	Existing cant 
	Existing R
	Max alignment speed
	Min length of transition curve
	Theoretical Max speed
	Cant to be increased
	Future cant value

	 
	 
	 
	(cm)
	(m)
	(km/h)
	(m)
	(km/h)
	 
	(cm)

	Curve
	3806.623
	3806.740
	3
	1400
	115
	115.80
	110
	 
	 

	Curve
	3806.878
	3806.986
	1
	1400
	105
	106.15
	110
	yes
	2

	Curve
	3807.022
	3807.162
	4
	1900
	135
	123.33
	110
	 
	 

	Curve
	3816.950
	3817.221
	4
	2000
	140
	132.05
	110
	 
	 

	Curve
	3819.512
	3819.693
	9
	700
	100
	101.29
	90
	 
	 

	Curve
	3819.693
	3819.793
	9
	500
	90
	64.05
	90
	 
	 

	Curve
	3819.819
	3820.230
	11
	600
	95
	84.77
	90
	 
	 

	Curve
	3820.426
	3821.003
	10
	600
	95
	95.63
	90
	 
	 

	Curve
	3821.118
	3821.904
	10
	600
	95
	95.63
	90
	 
	 

	Curve
	3821.924
	3822.462
	9
	600
	90
	81.05
	90
	 
	 

	Curve
	3823.115
	3823.774
	7
	750
	95
	87.36
	90
	 
	 

	Curve
	3823.788
	3824.114
	9
	600
	90
	81.05
	90
	 
	 

	Curve
	3830.631
	3831.298
	3
	2030
	135
	126.91
	110
	 
	 

	Curve
	3834.580
	3834.963
	6
	1800
	140
	121.84
	110
	 
	 

	Curve
	3835.838
	3836.140
	5
	1900
	140
	126.38
	110
	 
	 

	Curve
	3840.875
	3841.731
	4
	2000
	140
	132.05
	110
	 
	 

	Curve
	3856.257
	3856.666
	9
	600
	90
	81.05
	90
	 
	 

	Curve
	3857.907
	3858.279
	8
	600
	90
	91.34
	90
	 
	 

	Curve
	3870.010
	3870.685
	9
	600
	90
	81.05
	90
	 
	 

	Curve
	3872.065
	3873.272
	8
	600
	90
	91.34
	90
	 
	 

	Curve
	3873.307
	3873.649
	9
	600
	90
	81.05
	90
	 
	 

	Curve
	3876.122
	3876.447
	10
	640
	95
	82.87
	90
	 
	 

	Curve
	3878.332
	3878.510
	3
	1600
	120
	113.18
	90
	 
	 

	Curve
	3880.460
	3880.787
	4
	1900
	135
	123.33
	90
	 
	 

	Curve
	3884.637
	3884.934
	10
	300
	65
	56.53
	60
	 
	 

	Curve
	3885.284
	3885.573
	6
	500
	75
	69.14
	60
	 
	 

	Curve
	3885.694
	3885.870
	8
	400
	70
	58.54
	60
	 
	 

	Curve
	3885.870
	3886.004
	8
	1200
	125
	118.30
	60
	 
	 

	Curve
	3887.913
	3888.565
	6
	1000
	105
	93.42
	60
	 
	 

	Curve
	3890.620
	3891.013
	8
	600
	90
	91.34
	60
	 
	 

	Curve
	3891.152
	3891.381
	8
	400
	70
	58.54
	60
	 
	 

	Curve
	3891.432
	3891.571
	5
	600
	80
	76.23
	60
	 
	 

	Curve
	3891.657
	3891.869
	6
	330
	60
	52.39
	60
	 
	 

	Curve
	3891.872
	3892.156
	8
	320
	70
	 
	60
	 
	 

	Curve
	3892.203
	3892.306
	1
	500
	60
	54.87
	60
	 
	 

	Curve
	3892.441
	3892.576
	4
	400
	60
	49.74
	60
	 
	 

	Curve
	3892.576
	3892.699
	4
	700
	85
	86.51
	60
	 
	 

	Curve
	3892.836
	3893.219
	8
	800
	100
	87.20
	60
	 
	 

	Curve
	3893.276
	3893.507
	9
	300
	65
	63.96
	60
	 
	 

	Curve
	3893.513
	3893.716
	6
	500
	75
	69.14
	60
	 
	 

	Curve
	3893.717
	3893.916
	8
	320
	70
	 
	60
	 
	 

	Curve
	3894.001
	3894.224
	9
	900
	110
	98.19
	60
	 
	 

	Curve
	3894.224
	3894.695
	9
	300
	65
	63.96
	60
	 
	 

	Curve
	3894.751
	3895.065
	9
	309
	65
	60.15
	60
	 
	 

	Curve
	3895.146
	3895.734
	6
	500
	75
	69.14
	60
	 
	 

	Curve
	3895.649
	3895.829
	9
	300
	65
	63.96
	60
	 
	 

	Curve
	3895.858
	3896.047
	5
	600
	80
	76.23
	60
	 
	 


	Rehabilitation works for Lugovaya-Balykchi Line - Kazakh border-Balykchi section 3/4

	Existing and future line speed limits - curves modifications

	Existing situation
	"with project" situation

	Curves
	 
	 
	Existing cant 
	Existing R
	Max alignment speed
	Min length of transition curve
	Theoretical Max speed
	Cant to be increased
	Future cant value

	 
	 
	 
	(cm)
	(m)
	(km/h)
	(m)
	(km/h)
	 
	(cm)

	Curve
	3896.109
	3896.344
	8
	300
	60
	48.03
	60
	 
	 

	Curve
	3896.370
	3896.776
	10
	300
	65
	56.53
	60
	 
	 

	Curve
	3896.809
	3897.138
	10
	300
	65
	56.53
	60
	 
	 

	Curve
	3897.353
	3897.447
	1
	2200
	130
	127.84
	60
	 
	 

	Curve
	3897.638
	3898.138
	4
	500
	70
	66.03
	60
	 
	 

	Curve
	3897.776
	3898.037
	9
	300
	65
	63.96
	60
	 
	 

	Curve
	3898.046
	3898.322
	6
	300
	55
	41.54
	60
	yes
	7

	Curve
	3898.274
	3898.428
	2
	1000
	90
	83.60
	60
	 
	 

	Curve
	3898.696
	3898.851
	1
	450
	55
	46.54
	60
	yes
	2

	Curve
	3899.031
	3899.114
	2
	800
	80
	73.17
	60
	 
	 

	Curve
	3899.582
	3899.920
	4
	600
	75
	66.19
	60
	 
	 

	Curve
	3900.150
	3900.268
	2
	1600
	115
	109.54
	60
	 
	 

	Curve
	3900.267
	3900.339
	1
	1300
	100
	98.49
	60
	 
	 

	Curve
	3900.339
	3900.522
	2
	500
	65
	63.63
	60
	 
	 

	Curve
	3900.522
	3900.712
	2
	1400
	110
	110.71
	60
	 
	 

	Curve
	3900.767
	3900.882
	2
	400
	55
	46.86
	60
	yes
	3

	Curve
	3900.907
	3901.191
	10
	300
	65
	56.53
	60
	 
	 

	Curve
	3901.280
	3901.613
	2
	500
	65
	63.63
	60
	 
	 

	Curve
	3901.787
	3901.957
	6
	400
	65
	53.54
	60
	 
	 

	Curve
	3902.240
	3902.555
	5
	610
	80
	74.23
	60
	 
	 

	Curve
	3902.715
	3902.945
	8
	400
	70
	58.54
	60
	 
	 

	Curve
	3902.950
	3903.178
	10
	400
	75
	65.00
	60
	 
	 

	Curve
	3903.478
	3903.692
	4
	500
	70
	66.03
	60
	 
	 

	Curve
	3903.723
	3903.933
	6
	500
	75
	69.14
	60
	 
	 

	Curve
	3903.939
	3904.166
	8
	400
	70
	58.54
	60
	 
	 

	Curve
	3904.170
	3904.391
	5
	400
	65
	60.97
	60
	 
	 

	Curve
	3904.417
	3904.546
	6
	500
	75
	69.14
	60
	 
	 

	Curve
	3904.765
	3905.009
	8
	300
	60
	48.03
	60
	 
	 

	Curve
	3905.027
	3905.255
	8
	300
	60
	48.03
	60
	 
	 

	Curve
	3905.255
	3905.434
	7
	350
	65
	60.13
	60
	 
	 

	Curve
	3905.574
	3905.662
	2
	1050
	95
	94.97
	60
	 
	 

	Curve
	3905.683
	3905.741
	0
	600
	65
	65.40
	60
	 
	 

	Curve
	3905.741
	3905.870
	8
	310
	60
	44.71
	60
	 
	 

	Curve
	3905.891
	3906.165
	10
	300
	65
	56.53
	60
	 
	 

	Curve
	3906.224
	3906.540
	10
	300
	65
	56.53
	60
	 
	 

	Curve
	3906.600
	3906.841
	9
	300
	65
	63.96
	60
	 
	 

	Curve
	3906.867
	3907.037
	6
	300
	55
	41.54
	60
	yes
	7

	Curve
	3907.067
	3907.227
	4
	300
	55
	54.11
	60
	yes
	7

	Curve
	3907.351
	3907.573
	7
	300
	60
	54.89
	60
	 
	 

	Curve
	3907.606
	3907.791
	8
	300
	60
	48.03
	60
	 
	 

	Curve
	3907.798
	3908.012
	6
	300
	55
	41.54
	60
	yes
	7

	Curve
	3908.148
	3908.446
	7
	300
	60
	54.89
	60
	 
	 

	Curve
	3908.806
	3909.006
	7
	300
	60
	54.89
	60
	 
	 

	Curve
	3909.030
	3909.174
	3
	400
	60
	56.59
	60
	 
	 

	Curve
	3909.288
	3909.421
	2
	400
	55
	46.86
	60
	yes
	3

	Curve
	3909.425
	3909.537
	3
	400
	60
	56.59
	60
	 
	 

	Curve
	3909.662
	3909.786
	3
	400
	60
	56.59
	60
	 
	 


	Rehabilitation works for Lugovaya-Balykchi Line - Kazakh border-Balykchi section 4/4

	Existing and future line speed limits - curves modifications

	Existing situation
	"with project" situation

	Curves
	 
	 
	Existing cant 
	Existing R
	Max alignment speed
	Min length of transition curve
	Theoretical Max speed
	Cant to be increased
	Future cant value

	 
	 
	 
	(cm)
	(m)
	(km/h)
	(m)
	(km/h)
	 
	(cm)

	Curve
	3910.125
	3910.258
	7
	300
	60
	54.89
	60
	 
	 

	Curve
	3910.259
	3910.374
	6
	390
	65
	56.05
	60
	 
	 

	Curve
	3910.400
	3910.519
	7
	360
	65
	57.01
	60
	 
	 

	Curve
	3910.926
	3911.265
	3
	800
	85
	80.55
	70
	 
	 

	Curve
	3912.200
	3912.398
	4
	500
	70
	66.03
	70
	 
	 

	Curve
	3912.402
	3912.580
	9
	600
	90
	81.05
	70
	 
	 

	Curve
	3912.628
	3913.135
	7
	400
	70
	66.54
	70
	 
	 

	Curve
	3913.365
	3913.715
	8
	400
	70
	58.54
	70
	 
	 

	Curve
	3913.737
	3914.041
	8
	400
	70
	58.54
	70
	 
	 

	Curve
	3915.453
	3915.610
	1
	2000
	125
	125.26
	70
	 
	 

	Curve
	3917.020
	3917.412
	7
	530
	80
	74.05
	70
	 
	 

	Curve
	3917.715
	3918.265
	9
	450
	80
	80.30
	70
	 
	 

	Curve
	3917.865
	3917.999
	10
	300
	65
	56.53
	60
	 
	 

	Curve
	3918.018
	3918.219
	7
	330
	60
	45.54
	60
	 
	 

	Curve
	3918.404
	3918.605
	7
	830
	100
	92.17
	60
	 
	 

	Curve
	3918.693
	3919.021
	9
	360
	70
	64.15
	60
	 
	 

	Curve
	3919.201
	3919.363
	8
	300
	60
	48.03
	60
	 
	 

	Curve
	3919.640
	3920.025
	6
	600
	80
	67.08
	60
	 
	 

	Curve
	3920.140
	3920.520
	10
	290
	65
	61.04
	60
	 
	 

	Curve
	3920.520
	3920.821
	10
	320
	 
	 
	60
	yes
	 

	Curve
	3920.898
	3921.066
	6
	400
	65
	53.54
	60
	 
	 

	Curve
	3921.151
	3921.350
	11
	370
	75
	68.65
	60
	 
	 

	Curve
	3921.350
	3921.552
	9
	480
	80
	70.14
	60
	 
	 

	Curve
	3921.686
	3922.043
	7
	650
	90
	88.27
	60
	 
	 

	Curve
	3922.200
	3922.371
	1
	2000
	125
	125.26
	60
	 
	 

	Curve
	3922.497
	3922.667
	6
	450
	70
	60.92
	60
	 
	 

	Curve
	3922.734
	3923.257
	7
	460
	75
	71.06
	60
	 
	 

	Curve
	3926.302
	3926.536
	3
	700
	80
	77.09
	60
	 
	 

	Curve
	3926.678
	3926.889
	6
	400
	65
	53.54
	60
	 
	 

	Curve
	3926.916
	3927.282
	8
	250
	55
	44.82
	60
	yes
	9

	Curve
	3927.484
	3927.600
	4
	1300
	115
	114.60
	70
	 
	 

	Curve
	3927.600
	3927.738
	6
	500
	75
	69.14
	70
	 
	 

	Curve
	3928.916
	3929.305
	6
	620
	85
	83.26
	70
	 
	 

	Curve
	3929.759
	3930.351
	7
	500
	75
	60.57
	70
	 
	 

	Curve
	3930.806
	3931.089
	17
	300
	75
	55.25
	70
	 
	 

	Curve
	3931.136
	3931.337
	3
	1000
	95
	89.94
	70
	 
	 

	Curve
	3931.464
	3931.839
	11
	300
	65
	49.10
	70
	yes
	12

	Curve
	3932.243
	3932.469
	6
	400
	65
	53.54
	70
	yes
	7

	Curve
	3932.716
	3932.968
	4
	900
	95
	92.70
	60
	 
	 

	Curve
	3933.902
	3934.217
	8
	550
	85
	81.85
	60
	 
	 

	Curve
	3934.583
	3934.787
	9
	260
	60
	57.00
	60
	 
	 

	Curve
	3934.789
	3934.900
	3
	290
	50
	44.45
	60
	yes
	5

	Curve
	3934.900
	3935.068
	5
	600
	80
	76.23
	60
	 
	 

	Curve
	3935.331
	3935.853
	4
	1000
	100
	97.18
	60
	 
	 

	Curve
	3936.126
	3936.411
	5
	600
	80
	76.23
	60
	 
	 

	Curve
	3938.272
	3938.583
	2
	1500
	110
	101.65
	60
	 
	 

	Curve
	3941.959
	3942.399
	3
	2000
	135
	129.50
	60
	 
	 

	Curve
	3946.662
	3947.137
	5
	600
	80
	76.23
	60
	 
	 

	Balykchi
	3947.175
	3948.683
	 
	 
	 
	 
	 
	 
	 


2.2 Stations 

General

The approved solution doesn’t consider interventions within stations but those related to the track. Notwithstanding that a description is here below given.

The line Bishkek-Balykchi is provided with 17 stations with a distance between 37 (longest section) and 4 km. Their main functions are:

· operation (train crossings and overcoming);

· train parking;

· rolling stock (for service, for shunting or for maintenance) parking;

· passenger service;

· link for branches.

The following table 2.2-1 resumes the stations position and distances on the Bishkek-Balykchi line.

Table 2.2 – 1 Stations on the Kazakh border-Bishkek-Balykchi line

	Rehabilitation works for Lugovaya-Balykchi Line - Kazakh border-Balykchi section

	Stations

	 
	Station name
	Dimension (number of tracks)
	kind of station
	centre building chainage
	Distance (km)

	 
	
	
	
	
	 

	 
	Kazakh border
	
	
	3687.280
	 

	 
	
	
	
	
	16.042

	1
	Kaindi
	5
	medium
	3703.322
	 

	 
	
	
	
	
	14.920

	2
	Kara-Balta
	7
	large plant
	3718.242
	 

	 
	
	
	
	
	12.666

	3
	R-141
	4
	small/petroleum
	3730.908
	 

	 
	
	
	
	
	9.184

	4
	Belovodskaja
	6
	large plant
	3740.092
	 

	 
	
	
	
	
	15.343

	5
	Shopokovo
	5
	medium
	3755.435
	 

	 
	
	
	
	
	9.777

	6
	Soklukh
	3
	small
	3765.212
	 

	 
	
	
	
	
	10.379

	7
	Bishkek - I
	 
	large plant
	3775.591
	 

	 
	
	
	
	
	4.471

	8
	Bishkek - II
	5
	medium
	3780.062
	 

	 
	
	
	
	
	3.853

	9
	Alamedin
	7
	large plant
	3783.915
	 

	 
	
	
	
	
	16.654

	10
	Kant
	6
	large plant
	3800.569
	 

	 
	
	
	
	
	18.521

	11
	Ivanovka
	5
	medium
	3819.090
	 

	 
	
	
	
	
	20.478

	12
	Tokmak
	11
	large plant
	3839.568
	 

	 
	
	
	
	
	31.953

	13
	Bystrovka
	5
	medium
	3871.521
	 

	 
	
	
	
	
	12.815

	14
	Djil-Aryk
	6
	medium
	3884.336
	 

	 
	
	
	
	
	15.324

	15
	R-148
	2
	small
	3899.660
	 

	 
	
	
	
	
	37.281

	16
	Kojamat-Kurkol
	3
	small
	3936.941
	 

	 
	
	
	
	
	10.816

	17
	Balykchi
	11
	large plant
	3947.757
	 

	 
	end of station
	 
	 
	3948.683
	0.926


2.3 Level Crossings

Along the Kazakh border-Bishkek-Balykchi railway section a total of 52 level crossings is present.

The level crossing protection system is only assured by crossing warning signals (traffic lights and Saint Andrew crosses) without barriers.

The warning signalling system is automatic: track circuits detect trains and activate warning indications at level crossings.

Usually in correspondence of the level crossings there are unpaved tracks and not proper roads. The pavement of the level crossing area is typically made of concrete blocks or rarely of wooden beams.

From general experience, the level of safety afforded by these devices on their own is insufficient. In the specific case of the Kazakh border-Biskek-Balicki railway line this protection system could be justified by the low intensity of rail traffic and by the trifling volume of road traffic.

Hereafter is listed the position of each level crossing:

Table 2.3-1
	Kazakh border-Balykchi line

	Level Crossings

	1
	L.C.
	3690.142

	2
	L.C.
	3691.960

	3
	L.C.
	3698.967

	4
	L.C.
	3702.417

	5
	L.C.
	3705.425

	6
	L.C.
	3712.066

	7
	L.C.
	3715.900

	8
	L.C.
	3717.088

	9
	L.C.
	3720.169

	10
	L.C.
	3722.456

	11
	L.C.
	3724.100

	12
	L.C.
	3726.617

	13
	L.C.
	3733.964

	14
	L.C.
	3737.029

	15
	L.C.
	3739.861

	16
	L.C.
	3741.943

	17
	L.C.
	3747.418

	18
	L.C.
	3756.079

	19
	L.C.
	3761.310

	20
	L.C.
	3769.560

	21
	L.C.
	3771.950

	22
	L.C.
	3777.041

	23
	L.C.
	3778.094

	24
	L.C.
	3779.461

	25
	L.C.
	3787.064

	26
	L.C.
	3791.261

	27
	L.C.
	3799.215

	28
	L.C.
	3801.224

	29
	L.C.
	3804.717

	30
	L.C.
	3807.295

	31
	L.C.
	3812.417

	32
	L.C.
	3819.522

	33
	L.C.
	3826.695

	34
	L.C.
	3832.903

	35
	L.C.
	3836.792

	36
	L.C.
	3838.447

	37
	L.C.
	3841.151

	38
	L.C.
	3844.947

	39
	L.C.
	3848.263

	40
	L.C.
	3852.476

	41
	L.C.
	3857.771

	42
	L.C.
	3864.543

	43
	L.C.
	3868.028

	44
	L.C.
	3872.189

	45
	L.C.
	3876.830

	46
	L.C.
	3884.634

	47
	L.C.
	3888.891

	48
	L.C.
	3892.621

	49
	L.C.
	3898.928

	50
	L.C.
	3925.116

	51
	L.C.
	3938.255

	52
	L.C.
	3946.590


2.4 Geology of the line

The main section of the railway line, from the Kazakh border to approximately Djil Arik, is basically situated on flat areas presenting, however, a general, regional inclination to the north, towards the Chu river.

These areas, extending between the Kyrgyz range, at South and the Chu river, at North, are part of the vast southern extension of the catchment area of this river, tributary of the large Issyk – Kul interior basin. 

Geologically said areas are mainly composed of Neogene molasse and Quaternary alluvial fans and alluvial sediments deposited by the numerous mountains rivers discharging from the Kyrgyz range to the north, as tributaries of the Chu river.

The groundwater and acquifers of these Quaternary sediments are recharged both by atmospheric precipitation and by river water infiltration.

Past Djil Arik the railway enters into mountainous areas, following the Chu River valley up to reach Balikchy, at the western edge of the Issik Kul Lake.

No critical engineering geological conditions for the existing railway have been observed along the Kazakh border – Bishkek section, while a more deep analysis has been performed for the Bishkek-Balikchi section.

The general geological configuration of the Bishkek – Balikchi railway section is examined on the basis of the available geological map of the Kyrgyz Republic and of the observations carried out during the site visits.

The section may be analysed according to the following three separate portions:

1. Bishkek – Djil Ariyk portion

2. Djil Ariyk – Koiamat portion

3. Koiamat – Balikchi portion.

1.
Bishkek – Djil Aryk

The railway line runs in W-E direction on the quaternary plains extending south of the Chu River. The plains are formed by the alluvial deposits and alluvial terraces both of the Chu River and of the numerous rivers discharging from the mountains range at South. These alluvial sediments are composed of alternations of sands, gravels and pebbles of different petrographic nature, and include also silt and clays layers.

2.
Djil Ariyk – Koiamat

Beyond Djil Aryk the line turns southwards following the bottom of the Chu river valley, that crosses the mountains range from North to South.

West of the river the mountains range has a latitudinal direction, developing westwards into the Kirkyzskij range. East of the river the direction of the mountains range changes to SW-NE, developing into the Kungey Alatau range, at the North of Issyk Kul lake.

The valley sides are generally formed by steep slopes, where the observed bedrock includes the following geological formations:

· Tertiary sedimentary rocks (sandstones, conglomerates, carbonates, marles and claystones);

· Pre-mesozoic sedimentary and volcanic rocks (sandstones, conglomerates, carbonates, andesites, basalts, porphyrites, tuffs)

· Pre-mesozoic intrusive formations (mainly Permian granitic formations)

The above formations are intensively folded and faulted and, particularly the most competent rocks, are always densily jointed.

3
Kojamat/Kurkol – Balikchi

Before reaching Kojamat/Kurkol the Chu River turns to East and the valley widens considerably, joining the plain of Balikchi, while the river turns again to South.

This large, flat part of the Chu valley and the adjoining plain of Balikchi are formed by alluvial deposits including recent alluvial and quaternary terraces composed of alternating sands, gravels and pebbles that covers the bedrock.

2.5 Structures and Drainages

Along the entire Lugovaya-Balykchi line there are 3 steel bridges, the longest one between Djil Aryk station and R148 (see Table 2.5 – 1) and 132 concrete bridges (see Table 2.5 – 2).
Table 2.5 – 1 - Steel bridges

	Steel bridges

	Span
	Length
	number

	(n)
	(m)
	(n)

	1
	26
	1

	1
	64
	1

	1
	9,8
	1


Table 2.5 – 2 - Concrete bridges

	Concrete bridges 

	Span
	Length
	number

	(n)
	(m)
	(n)

	1
	2,13
	28

	2
	2,13
	1

	1
	4,27
	20

	2
	4,27
	13

	1
	6,40
	8

	2
	6,40
	8

	3
	4,22
	3

	3
	6,40
	1

	2
	8,53
	3

	4
	4,27
	1

	3
	2,53
	1

	1
	8,53
	2

	4
	2,60
	1

	1
	0,50
	2

	3
	8,53
	1

	5
	6,40
	2

	1
	15,80
	1

	3
	7,90
	1

	2
	9,90
	2

	1
	10,00
	1

	1
	11,00
	2

	3
	15,30
	1

	2
	12,50
	1

	3
	10,00
	1

	2
	10,00
	1

	2
	14,00
	1

	1
	3,00
	2

	2
	5,00
	1

	1
	1,00
	4

	3
	7,30
	1

	1
	2,00
	6

	1
	4,00
	6

	1
	6,00
	1

	1
	7,90
	2

	1
	5,00
	1

	2
	7,90
	1

	
	
	132


The number of pipe culverts, box culverts and arch culverts is indicated in Table 2.5 – 3.

Table 2.5 – 3 - Culverts
	Pipe culverts
	
	Box culverts
	
	Arch culverts

	Pipes
	number
	
	Boxes
	number
	
	 
	number

	(n)
	(n)
	
	(n)
	(n)
	
	 
	(n)

	1
	204
	
	1
	24
	
	 
	164

	2
	28
	
	2
	11
	
	
	

	3
	2
	
	
	
	
	
	

	>3
	2(*)
	
	
	
	
	
	

	(*) 5 and 8 pipes
	
	
	
	
	
	


Five concrete bridges need rehabilitation works.

After the station of Djil Aryk on the way to Balykchi a bridge, crossing a left tributary of Chu river, presents some particular problems occurred during the last flood (see Fig. 2.5 - 1). 

Fig. 2.5 – 1 – Bridge after Djil Aryk

[image: image12.jpg]



At the bridge location the river bed is composed of recent alluvial sediments, while the river banks, few meter high, are cut through quaternary alluvial/colluvial terraces composed of gravels, pebbles and rock debris of various nature in abuntant sandy – silty reddish matrix.

Evidence of scouring activities are present both on the bed and on the banks of the water course. The last flood has damaged one of the bridge abutments when the water over-flew the concrete channel coming from an upstream earth-fill dam. The reservoir of this dam is however completely filled up with alluvial and colluvial materials sedimented into the basin; therefore the channel, probably designed as the dam spillway with the function of controlling the floods discharge from reservoir, appears to have concluded is life.

Fig. 2.5 – 2 - Old concrete channel along the river bed

[image: image13.jpg]



A second bridge, which needs rehabilitation works, is located between the stations of Kant and Ivanovka, crossing Konda river, a left tributary of Chu river (Fig. 2.5 - 3).

Fig. 2.5 – 3 - Bridge on Konda River

[image: image14.jpg]



The bridge has a 2x6m scheme: 2 spans, each of them equipped with 2 beams 6 meters long.

The bridge piers need rehabilitation works and beams in bad conditions have to be replaced. However the abutments and piers foundations appear adequately safeguarded against river scouring by the existing rock walls protection of the river banks and the concrete weir across the stream.

The above mentioned interventions are similar to those needed for other three bridges located at the chainages km 3694+10, 3708+5, 3765+6, on Bishkek-Balykchi section. 

2.6 Avalanche shed

On the Balykchi – Bishkek section, between the station of Djil Arik and R148 block post, two avalanche sheds are located.

The structures has been realised with a retaining wall of irregular concrete blocks, upstream, and pillars realised with regular concrete blocks fixed in a hole having the same size of the pillar, downstream. A concrete slab as roofing and foundations not connected by beams complete the structure. The link between pillars and foundations is implemented with the so-called “glass system”, without armature, while the edge beams simply lay on the top of pillars.

The stability of the described structures has to be considered critical, seeming sufficient for the line protection against land slides and falling rocks, but inadequate to bear the horizontal actions due to the earthquakes.

On the mountain side of the first avalanche shed a landslide occurred, after rains during past winter (see Figure 2.6 - 1). 

The geological formations involved in the landslide appear to be poorly cemented reddish conglomerate, red clay and sand, probably of Neogene age (see Figure 2.6 - 2).

Figure 2.6 - 1 – Avalanche shed with landslide on the back

[image: image15.jpg]



Apparently the landslide is pushing on the reinforced concrete back-wall of the shed, however no signs of disruption or damages are visible on the wall. Pools of water were present on the surface of the slide area during the site visit (see Figure 2.6 – 3) but drainage wells built from the same wall and reported to be about 10 meters deep, were dry.

Figure 2.6 - 2 – Closer view of the landslide

[image: image16.jpg]



Figure 2.6 - 3 – Pools of water on the landslide surface

[image: image17.jpg]



Considering the criticality of the situation, the Consultant strongly recommends to implement prevention measures against the possibility of further development of the landslide. These measures should possibly include the following works:

· remodelling of the slope shape, by reducing the soil load at the head and possibly enlarging it at the toe of the landslide;

· surface drainage of the slide area by means of a drainage ditches of adequate dimensions and gradient for discharging rain water;

· subsurface drainage with the use of subsurface drainage borings.

The structure of the second avalanche shed has been constructed in part and then stopped for shortage of funds (see Figure 2.6 – 4).

Considering the immanent risk of rock falls from the steep slopes uphill of the railway, the completion of this shed should be urgently implemented.

The related civil works for the completion of the avalanche shed are included in Lot 3.4.

Figure 2.6 - 4 – Disconnected rock slope above the avalanche shed

[image: image18.jpg]



2.7 Ballast quarry

The Consultant’s experts visited the only quarry in Kyrgyzstan in service for production of ballast for railways. Kyrgyz Railways are the owners of the plant and entitled to exploit the concession.

The quarry is located near the station of Djil Aryk. The quarried material is a pink coloured, good quality granitic rock, fine-medium and medium grained, affected by variously oriented, dense jointing systems (see Figure 2.7 - 1). The joints disconnect the rock mass into blocks of dimensions ranging from approximately few dm to more than 1 m3. 

According to information obtained on site, the quarry concession regards an estimated total quantity of material of 100.000 m3, but very big quantities of material of the same quality exist nearby.

Figure 2.7 - 1 – Quarried granitic rock

[image: image19.jpg]



The existing crushing plant is basically composed of a jaw breaker for the primary crushing of the quarried rock to obtain ballast material and of a gyratory breaker for the secondary crushing, to obtain sub ballast material.

Figure 2.7 - 2 – Existing crushing plant

[image: image20.jpg]



Conveyer rubber belts on straight rollers transport the material from one breaker to the other. Between the two breakers a screening station, with rotary screens, selects and separates the different materials. The coarser portion of the material (ballast) is transported to the stocking area through the conveyer belts, while the remaining portion is conveyed to the gyratory breakerfor the secondary crushing. Again a screening station downstream of the gyratory breaker selects and divides the sub ballast material from the finer material (sand and grit). The sub ballast is then conveyed to separate stock areas.

From the preliminary examination of the plant and considering the granitic nature of the rock, rich in quartz, a high degree of wearing of the crushing machinary may be expected; more particularly, not considering the engines of the various apparatuses, the components of the plant mostly subjected to wearing are:

· the shell that covers the jaws of the jaw breaker and the internal elements of the giratory breaker (hammers and internal shells);

· the conveyers rubber belts;

· the straight rollers, mainly those adjacent and below the screening and crushing stations;

· the metallic net of the screening system;

· the ball bearing of the engines (crushing and screening system);

· all the electrical apparatuses  (electric panel and cables);

· wells and washing system (if existent).

Finally it has to be remarked that the crushing plant appears under utilized: 250 m3 possible daily production against only 12000 m3 of yearly production for track maintenance.

3. Description of the designed improvements

The envisaged works for line rehabilitation are as follow: 

a. Civil works concerning earthworks;

b. Permanent way replacing works;

c. Existing permanent way rail welding and tension regulation;

d. Re-alignment, leveling and ballast cleaning on the existing sections;

e. Civil works concerning structures (bridges and avalanche shed);

f. Civil works concerning re-pavement of some level crossings (L.C.). In terms of level crossings no elimination has been envisaged for the low traffic both on the railway line and on the interfered roads (mainly unpaved roads).

The following Table 3-1 gives a short description of the different works.

Table 3-1 – Infrastructures works for line rehabilitation
	Code
	Works
	Description

	1A
	Topographic survey of the line and corrections of the existing alignment and profile.
	Topographic survey to be carried out along the line, for a strip of 50+50m around the existing railway axis, production of the current status cartografy, and detailed correction of the alignment and profile of the line. New plan profile in scale 1:1,000 and current cross sections of the line in scale 1:200-1:100 step 50 m will be produced, indicating the existing and future geometrical parameters of the line.

	2A
	Demolition of line.
	It consists in dismantling the existing worn out permanent way (rails, junctions, sleepers and fastenings), transportation of the materials to the deposit sites, dividing them into old and re-usable materials (residual value). This operation will be presumably carried out according to the methodology developed in this area: after having manually eliminated the fish-plated junctions of the rails, the dismantling train will pass over the free track panels, and its tail equipped with a dismantling crane will dismantle the track panels and automatically transport them into the front platform wagons.

	3A
	Excavation. 
	After having dismantled the permanent way, excavation of about 50-60 cm of topping material of the embankment by means of machine (bulldozer with front shovel). Generally, during this process, old polluted ballast and old polluted sub-ballast (sandy gravel) are discharged on embankment side for their future re-use. In case this work takes place into stations, the removed top material will be transported to dump. This item also include the further compaction of the top layer of the embankment for increasing hits bearing capacity and for re-shaping the embankment roof.

	4A
	Partial lateral rebuilding embankment section, placing and compacting the removed top material for widening the top surface of about 1,0 m on both sides.
	This item will be applied only on those sections where the existing embankment is found to be eroded and not compliant with the typical cross section. In many cases in fact, ballast is falling on the embankment side for the embankment is reduced in transversal dimensions due to the water and wind erosion of hits slopes, not protected by means of grassing. For this item, material will be taken from the side material demolished in Item 3A for those sections where 3A took place, while for the other sections material will be transported or taken from the surrounding environment after tests. In order to widen the embankment side, the existing eroded side will be shaped in steps, and the additional earth will be added in layers of max 20-30cm in order to compact it by means of manual vibro-compacting machine.

	5A
	Implementation of a layer of sandy gravel material, 0,2 m thick under sleepers (sub-ballast). 
	After the item 4A, on the compacted top layer of the embankment the new layer of sandy gravel (sub-ballast) will be laid and compacted in the correct shape, according to typical cross section.

	6A
	Construction of line. 
	After the item 5A, the new track will be built (sleepers, fastenings and rails), by laying it on the sub-ballast layer. This procedure will be presumably carried out with the system used in this area, described in detail in the Figure on the next page. This system is based on the use of construction train, similar to the dismantling train, with opposed operations. Tail locomotive of this train will push the front laying crane against the section to be built, and the crane will lay track panels, casted outside of the field, on the sub-ballast layer. Provisional junctions will be installed and the construction train will run on the just installed panels. Construction of the line can also be carried out with other methods, as for example that envisaging the use of long welded rail to be laid on the two sides of the existing permanent way and the transportation of the sleepers only on the construction train. This second method allows to avoid the big number of weldings to be done on field and allows to transport on field sleepers and long rails separately. The first train transporting long rails would also run during line operation, laying the new rails on the two sides, the second train would dismantle the existing permanent way, cleaning and re-laying the sub-ballast, laying the sleepers (transported by its wagons) at the correct distance and it would finally install the lateral new rails on the sleepers, with fastenings. In the next pages the two envisaged construction methodologies will be described with schematic drawings. The item 6A also includes first layers ballast spreading, tamping and lifting of rails up to 3 cm to final level.

	7A
	Flash-butt or thermic weld of P65 rail. 
	Welding of the panels by means of flash-butt or thermic system. Welding of the rails will have to be done according to strict technical specifications, that will be detailed in the next phase of the study.

	8A
	Regulation of mechanical tension of long welded rails (l.w.r.). 
	After the rail welding, mechanical tensions will be regulated, according to strict technical specifications, that will be detailed in the next phase of the study.

	9A
	Final tamping and levelling of new line.
	The permanent way, so welded and regulated, will be in this phase taken to its final level and alignment by means of final tamping and levelling.

	10A
	Ballast cleaning on the other existing sections.
	On some of the sections where existing permanent way is preserved, ballast cleaning will be carried out. Ballast cleaning concerns the existing section ballast cleaning and re-shaping, with some addition of new ballast where necessary. It can be carried out by means of automatic machines or by handwork.

	11A
	Tamping, levelling and aligning the other existing sections with l.w.r. 
	All over the sections where existing permanent way is preserved, tamping, levelling and aligning will be carried out for reaching the final alignment.

	13A
	Excavation of ditches.
	Hydraulic drainages must be cleaned and embankment side ditches must be excavated when absent, in order to protect the embankment side from water infiltration and foot erosion. In general, no concrete cover is requested for the ditches. Trapezoid ditch 0.5-0.5-0.5 has a volume of 0,5m3/m.

	14A
	Pavement of level crossings.
	This item concerns the reconstruction of the pavement of the level crossings for the area of railway crossing only. It has been estimated that each level crossing envisages an area of about 50m by 10m.

	22A
	Renewal of bridges beams 
	Replacement of beams and base plates

	23A
	Maintenance of piers and abutments
	Rehabilitation of reinforced concrete structures, and of masonry and stone pitching works on the abutments.

	26A
	Construction of avalanche shed
	Completion of avalanche shed and measures to improve the existing sections: connecting the plinth with reinforced concrete foundation beams and doing the same thing at the head of the pillars.

	27A
	Quarry rehabilitation
	Upgrading of the ballast quarry up to the production needed to the Kyrgyz Railways for rehabilitating the line section.


The adopted option by the Feasibility Study considers that all activities (but major civil works like for the bridges and for the avalanche shed) will be basically carried out by the Kyrgyz Railways personnel during a sort of extraordinary maintenance which will be possible after purchasing materials, machines and plants.

Therefore four Lots have been considered for international tendering:

· Lot 3.1 – Purchase of machines

· Lot 3.2 – Purchase of Permanent Way materials

· Lot 3.3 – Purchase of a sleeper factory

· Lot 3.4 – Civil works

Lot 3.4 also includes the rehabilitation of the ballast quarry near Djil Aryk in order to reach a proper level of efficiency and increase the production needed for the rehabilitation of the railway track.

Thus Lots 3.1 and 3.2 regard the purchase of those materials and machines which are needed for the rehabilitation works carried out directly by the Kyrgyz Railways. Lot 3.3 is for purchase of a sleeper factory and Lot 3.4 regards civil works (bridges, avalanche shed and quarry rehabilitation) both will be performed by a Contractor under a Design-Build and Turnkey contract.

As the works will be mainly carried out by the Kyrgyz Railways as extraordinary maintenance, for such maintenance there is not need to details more the methodology of works while materials standards are duly described in the Technical Specification for Lot 3.2 (Purchase of permanent way materials).

The Consultant has deemed important to detail more some specific methodologies for the implementation possibly introducing European methodology or comparing European methodology with the CIS methodology.
3.1 Methodology for the line construction (Permanent Way)

3.1.1 Methodology 1

Hereafter the procedure commonly used in Europe to implement these works with heavy machines is described (see also Figure 3.1.1-1 here attached):
Figure 3.1.1-1


[image: image21.wmf]positioner

5) The positioner put the auxiliary rails on the concrete sleepers to form the new track.

4) The gantry cranes lay down the concrete sleepers

demolished panels

ballast train

tamping machine

profiler

1)New rails are laid down along track to be first used as service track for gantry cranes.

3) The gantry cranes dismantle the first panel, previonsly disjointed.

2) Normal composition of work train.

demolished panels

OLD TRACK

wagons to be loaded with demolished panels

NEW RAILS

(service track)

concrete sleepers

gantry cranes

beam

aseiliary rails

1000m

METHODOLOGY 1 FOR TRACK REPLACEMENT

NEW TRACK

25m


Previous activities

I. the P65 rail bars 25 m long are welded in bars of 100÷125 m and staked,

II. the long P65 rail bars are loaded on platforms, transported and laid down along the line on both sides of the existing track,  positioned and jointed to be initially used as service track for portal cranes,

Activities to be done in the same day

III. a work train arrive at the beginning of the stretch scheduled to be  dismantled and rebuilt with P65 rails on concrete sleepers (in this case the average length of this stretch is 600 m per day). The work train is formed by:

·  platforms loaded with 2 self moving portal cranes and an ancillary beam;

· platforms to be loaded by dismantled 25 m track frames;

· platforms loaded with concrete sleepers to be installed.

IV. the portal cranes and ancillary beam, unloaded from the platforms, displace themselves on the service track, stop in correspondence of the first 25 m panel, previously disjointed from the adjacent ones, lift it and, coming back along the train, unload it on a flat wagon; this operations are repeated up to complete the dismantling of the scheduled length of track (see also item 2A);

V. the excavation of the existing materials start and go on until the design depth is reached (see also item 3A);

VI. the sandy-gravel material is spread on the surface between the service rails and compacted (see also item 5A);

VII. the portal cranes by means of the ancillary beam lift the concrete sleepers from wagons, run along the service track and lay down in two phases the concrete sleepers on the sandy gravel layer (distance between sleeper axles = 0,54 cm, that is 1840 sleepers per km are to be laid down) up to cover the full length of the dismantled stretch; at this stage reference stakes shall be used for locating the track CL and avoiding abnormal adjustments in a further stage;

VIII. the portal cranes and beam are re-loaded on their wagons,

After placing the polyethylene pads on the rail seats of the sleepers, using a little machine called “positioner” the P65 rails, forming the service track till the present phase, are put in their definitive position on the concrete sleepers and fastened; at this stage 50% of fastenings will be inserted, the joints shall be assured with additional bolts 

The new track shall be, manually and/or using the tamping machine, leveled, aligned and put in order to allow the passage of trains at a temporary speed limit of 10 km/h,

Activities to be done in the following period

IX. The long bars are welded up to a length of 400 m (temporary section); the joints may be welded by “thermic” or flash-butt process,

X. the finishing of the excavation and of the sandy gravel layer on  both external sides is implemented,

XI. about 1 m3  of ballast is laid down and the track lift of about  0,20 cm using the tamping machine and jacks,

XII. additional quantities of ballast are laid down  and the track is lift  up to reach a level of 0÷20 mm to the design level,

XIII. during the lay down of additional ballast, the lifting and tamping operation, the ballast section profile shall be adjusted by a  “profiler” machine, equipped with a brush for clearing the track,

XIV. before final lifting, straightening and leveling of the track, the following activities have to be carried out: the regulation of the mechanical stresses of the rails, the formation of the continuous welded rails (CWR), adjust the expansion joints and fix the 100% of the fastenings. 

XV. a final tamping of the complete track  has to be carried out, making use of an heavy tamping machine, at least 60 days after all the works described in the above paragraphs have been successfully completed.  The final line profiling has also to be implemented at this stage.

The individuation of number and type of machine to be purchased under Lot 3.1 has taken into account the just described methodology.

3.1.2 Methodology 2

Hereafter the procedure commonly used in CIS countries to implement these works with heavy machines is described (Figure 3.1.2-1, Figure 3.1.2-2, Table 3.1.2-1):

Fig 3.1.2 – 1 Main work schedule in the major repair works on track
[image: image22.jpg]



1 – preparing for charging and discharging of gravel-cleaning machine; 2 – securing the closure of the route section; 3 – preparing for dismantling; 4 - preparing for charging and discharging of gravel-cleaning machine; 5 – gravel cleaning; 6 – track rectification; 7 – unbolting the rail joints; 8 - dismantling of the track; 9 – gravel ploughing; 10 – track laying; 11 - bolting the rail joints; 12 – installing inventory stop brakes; 13 – setting the track on axle; 14 – gravel unloading; 15 – track rectification with VPО-3000 machine; 16 – equipping electrically-failed joints; 17 and 19 – exit of stop brakes; 18 – exhaust unit; 20 - track rectification; 21 - lining of the track; 22 – prism alignment.

Finally, the following table contains detailed timing of each phase of the works.

Table 3.1.2 – 1 Operational main work schedule in "possession"

	N.


	Operation name
	Planned time

	
	
	Duration

(min)
	End of operation,

Hours and minutes

	
	The passing of the last scheduled train on station
	
	10.40

	
	The work of the dismantling train
	
	

	1
	Arrival to the place of work
	15
	10.50

	2
	Positioning in running order
	8
	10.58

	3
	Dismantling of first packet (gravel-cleaning machine’s work start)
	12
	11.10

	4
	Dismantling of second packet
	12
	11.22

	5
	Same, third etc
	12
	11.34

	22
	Dismantling of twentieth packet
	12
	14.58

	23
	Positioning in transport order
	12
	15.10

	24
	Departure of dismantling train
	5
	15.15

	
	Gravel-cleaning machine’s work
	
	

	1
	Arrival on track
	5
	11.15

	2
	Gravel cleaning on the first section extending over 50 m (beginning of track laying)
	5
	11.20

	3
	Finishing gravel cleaning
	225
	15.00

	4
	Derailment
	5
	15.05

	
	Laying train work starts
	
	

	1
	Following to the place of work
	20
	11.10

	2
	Positioning in running order (start of laying)
	10
	11.20

	3
	First packet laying
	12
	11.32

	4
	Same, second etc
	12
	11.44

	22
	Twentieth packet laying
	12
	15.20

	23
	Exhaust unit positioning of crane in transport order
	10
	15.30

	24
	Departure for station
	3
	15.33

	
	Hoppers-dozers work
	
	

	1
	Following to the place of work of welded structure from 40 hoppers-dozers (start unloading)
	15
	13.00

	2
	Ballast unloading during track laying
	
	15.20

	3
	Unloading after track laying
	
	15.35

	4
	Departure of welded structure from 40 hoppers-dozers for station
	
	15.40

	
	The work of VPО-3000 machine
	
	

	1
	Following to the place of work
	15
	13.35

	2
	Charging
	5
	13.40

	3
	Machine’s work during gravel unloading
	
	15.40

	4
	The finishing of the measured shovel-packing
	
	15.55

	5
	Machine discharging and leaving for station
	5
	16.00

	
	Hoppers-dozers work
	
	

	1
	Following to the place of work
	15
	14.00

	2
	Ballast unloading
	
	16.15

	3
	Departure of welded structure from 40 hoppers-dozers for station
	
	16.20

	4
	Time route section is closed
	from 10. 40 until 16.40


Fig. 3.1.2 – 2 Current Permanent Way replacement cycle


[image: image23.wmf]1 - dismantling (distributor) train; 2 - packing (laying) train; T - disel locomotive;    

MPD - motor platform; YK - laying crane; BMC - balast dearer; XD - hopper-batcher; 

BPO - liner-tamper supfaser. 

MPD

T

X-D

1

BPO

YK

T

BMC

YK

Plasement of machines at work in free periods at capital repeir of track.

T

X-D

MPD

2

MPD

T


Previous activities

I. panels 25 meters long of concrete sleepers fastened to P65 rails are prepared in  a station near the work site and loaded on the laying train,

II. a dismantling train and a laying train (loaded with the new panels to be installed), coming from one of the adjacent stations, are placed astride the first panel to be dismantled; every train has a crane on the queue  of the composition, able to work  on the site of this panel,

III. the crane of the dismantling train lifts the first panel, whose joints have been previously unbolted, and, with a backward movement, lays it on a mobile device under crane on the platform wagon; this operation is repeated according to the possibilities given by the height of the crane, after a train displacing in successive positions correspondent to the other panels to be dismantled, 

IV. the mobile device, pulled by the rope of a winch, transfer on rollers the panels stacked on it to wagons in a rear position to allow the dismantling and stacking of more panels,

V. on the dismantled stretch, excavation works start, using ballast cleaner machine, soil moving machines, motor grader, pneumatic-tired roller, leveler, to prepare the new sandy-gravel layer, if it is foreseen  by the design, and /or a leveled ballast surface,

VI. the crane of laying train, lays down the 25 m long new panels assembled P65 rails fastened on concrete sleepers, and  provisional joints of panels are performed,

Activities to be done in the following period:

VII. new ballast is spread  along the line and the tamping machine start to compact ballast and to lift the rails up to 2÷3 cm from the design level,

VIII. rails are welded in 800 m bars and provisional joints recovered,

IX. during the lay down of additional ballast, the lifting and tamping operation, the ballast section profile shall be adjusted by a  “profiler” machine, equipped with a brush for clearing the track,

X. before final lifting, straightening and leveling of the track, the following activities shall be carried out: the regulation of the mechanical stresses of the rails, the formation of the continuous welded rails (CWR), adjust the expansion joints and fix the 100% of the fastenings.

XI. a final tamping of the complete track  has to be carried out, making use of an heavy tamping machine, at least 60 days after all the works described in the above paragraphs have been successfully completed.  The final line profiling has also to be implemented at this stage.

This methodology requires a number of machine and equipped wagons bigger than the previous one. Due to the shortage of efficient equipment of the Kyrgyz Railway it is suggested to adopt the previous methodology.

3.2 Methodology for rail welding

According to the information collected, the habit in CIS countries is not to weld rails on site but in the workshops. The length of the section to be considered is therefore limited by transport constraints (up to 800 m of long welded bars).

The European experience proves that rail welding can be performed on site by either of two methods:

· Thermic process

· Electric process

Within Lot 3.1 the purchase of a welding machine has been included.
3.2.1 Thermic welding

Type - The thermic welds shall be of the “rapid” type with prefabricated moulds and oxygen activated preheating.

Material and Equipment – The moulds shall be of the prefabricated type and suitable for P65 rails; they shall be stored in the cardboard boxes in which supplied.

The welding portions shall be of the type suitable for welding, with normal welding gaps, P65 rails in workshop or on site.

They shall be packed in sealed bags bearing in print the characteristic data: type of weld (“rapid”), type of rails and of steel. It is not allowed to use welding portions whose packaging has been tampered with and nothing shall be empirically added to or removed with welding portions. Should it be found necessary, in particular cases recognized as inevitable by the Works Director, to weld with wider gaps than specified, use shall be made of the appropriate welding portions.
Pre-heating shall be done by means of a suitable oxy-propane burner.

Particular care shall be taken in the storage of materials; the welding portions and the moulds shall be stored in a dry room away from inflammable materials; the oxygen cylinders and propane bottles shall be stored in isolated rooms and apart from each other. The welding equipment may be stored in the room were the welding portions and moulds are stored.

Operating procedures – The gap between the rail ends to be welded shall be between 15 and 16 mm or as specified by the manufacturer of the welding portions.  

The rail ends shall be perfectly aligned in both the horizontal and vertical plane. To compensate for lowering due to thermal contraction, the two rail end sections shall be raised by 1 mm. The alignment shall be maintained during welding by inserting steel wedges. The rail ends shall be cleaned with a wire brush and any moisture dried by using the burner.

The welding casting shall not be poured directly into the mould but through a casting pocket. The slag shall be collected in an appropriate box.

The burner shall be accurately centered on the welding gap and placed with the orifice 40 mm above the running surface of the rail.

During the pre-heating, the oxygen and propane pressures shall be respectively 5 kg/cm2 and 0.5 kg/cm2. The pre-heating shall last not less than 6 minutes.

The procedures for the subsequent operations, from the ignition of the portion through removal from the moulds, are left to the worker’s experience and skill.

The feed head may be removed by hammer and chisel or by a hydraulic press fitted with a suitably shaped chisel. The chiseling operation shall not result in the removal of material from the essential part of the welds.
The side surfaces and the running surface of the rail head shall be ground down by means of a suitable grinder to the normal rail profile.

On the remaining parts of the rail section the presence of the weld bead remaining from the chiseling operation shall be tolerated, after removal of the feed head and of the other superfluous parts of the weld casting, the welded joint shall be cleaned with a wire brush and protected by rust-proofing paint over a length of 20 cm.

Sample Testing and Checking

I. Moulds: visual inspection for integrity shall be performed on a 4% sample of each stock of welding moulds.

II. Portions: two portions chosen by the Works Director shall be taken from each stock and two welds shall be executed on two pairs of rail sections, each 0,75 m long, so as to obtain two samples with a welded joint.

III. Bending test: samples shall be subjected to the bending test in accordance with the following sketch:


[image: image24.wmf]1000

~1500

460

head

foot

Weld

P


Load P shall be increased slowly from 0 to 40 tons, continuously recording the deflection of the mid portion. Under the maximum load neither cracks nor fractures shall appear. After removing the load, the residual permanent deformation shall be measured one hour after the test.

IV. Internal sections: the specimen shall be cut through the center of the weld along a plane perpendicular to the longitudinal axis and then along the plane of symmetry of the rail sections. The sulphur print of the cross section shall be taken. Inspection of the sections shall show no cavities, internal damage or porosity.  At the Works Director’s absolute discretion, a light degree of porosity internally to the web and head may be tolerated.

V. Brinell hardness: on the longitudinal section, 5 mm under the surface the hardness shall be measured aver a 300 mm length. The Brinell hardness shall be comprised in the range of 20 units less to 40 units more than that measured on the steel of the original rail. The hardness test shall be performed with a steel ball 10 mm in diameter pressed against the steel with a load rising from 0 to 3000 dN in 30 second. The impression shall be spaced to 10 mm intervals.

VI. Other tests: any other test required by the Works Director with a view to determine the quality of the material used for thermic welding may be carried out. In the event of failure the weld shall be rejected. 

Manufacture Checks and Tests

Each stock of welding portion supplied shall be accompanied by a certificate issued by an official testing Institute of the manufacturer’s country, showing the results of the following tests performed on rail section welded with one of the portions from the stock, following the same procedures above outlined:

· bending test (see the preceding III. Paragraph)
· Brinell hardness (see the preceding IV. Paragraph)

· Sulfur prints of the weld cross section, and

· Chemical analysis which shall show that S and P contents not exceed each 0.05% and combined 0.09%.

Systematic Weld Checks

The following checks shall be performed on the welds executed in workshop or on the line:

· Visual check -  A perfectly straight ruler 1,0 m long, accurate to within 1/10 of 1mm, has to be used for lining and leveling the welded joint; the check shall be done over a length of 1 m centered on the weld and defects shall not exceed those shown in the drawing in Appendix 1,

· Visual check for the integrity of the weld,

· Ultrasound check by means of a special apparatus operating above the 3 MHz frequency

3.2.2 Electric Flash-butt Welding

Rail welding machine

The welds are executed by a welding machine that may operate either on track along the line or in the station yard.

The welding head shall be suitable for welding P65 rails and perform the following functions:

· grabbing the rail ends over a sufficient length to ensure good alignment and hold them tightened with great force for the entire duration of the process,

· heating the rail ends and bringing them to the upsetting state,

· upset-welding the rail ends with the necessary force,

· allowing the mechanical removal of the welding bead,

· leaving the rail with the joint in good alignment and condition.

All the welding process shall take place automatically without the intervention of the operators whose only jobs shall be to prepare the rails, remove the welding beads and finish the rail head surface.

After the mechanical removal of the bead produced by upsetting the head surfaces shall be finish-ground with a grinding machine, as required for the thermic welds.

For the acceptance of the welds the welding machine shall be equipped with a special apparatus recording the following data for any weld:

· current absorption,

· shortening of rails due to metal fusion,

· the batting force of the welding head.

Should the recording apparatus be out of order, no welding work will be allowed.

Sample Checking and Testing

Before beginning work, two sample welded joints shall be prepared, produced with the same welding machine which will be used for the work. The samples shall have the same characteristics as those prepared by thermic welding and shall be subjected to the following checks and tests:

· visual check with 1 m metal ruler of the same characteristics as that used to check thermic welds,

· bending test as that used to check thermic welds

· internal sections as that used to check thermic welds

· Brinell hardness check as that used to check thermic welds

The machine shall be accepted if the result of the tests and checks prove satisfactory and conform with the specifications. Otherwise the machine shall be adjusted and the tests repeated until satisfactory results are obtained. 

Systematic Weld Checks and Tests
Every flash-butt weld is subjected to:

a. visual checks as that described for thermic welds

b. integrity check

3.2.3 Formation of Continuous Welded Rails (CWR)

The purpose of forming CWR is to eliminate all rail joints and creating in the rails an even condition of thermal stresses in order to prevent thermal expansion (stress settling). The temperature at which the CWR is formed is called neutral temperature (zero stress at all points of the rail), hereinafter abbreviate as NT.

No CWR shall be formed on curves with a radius lower than 350 m and in stations where they will be formed according to Works Director’s instructions.

On the lines equipped with Automatic Block, the CWR is to be interrupted in correspondence of the signals and an insulated joint has to be installed to allow the correct work of the track circuits; towards and backwards two stretches 12,5 m long have to be formed using by means of two additional normal joints.

The CWR shall be formed at the NT.  The conditions required to get the NT may be obtained either naturally or artificially, i.e. by natural heating or with the use of tensors.

The temperature of the rail shall be monitored for at least one year and the NT lies in the range of + 7 oC -3 oC of the average temperature. The NT shall be fixed by the Works Director at the beginning of work.

Special rail thermometers suitable for measuring rail temperatures to within 1 oC have to be available.

The forming of the CWR shall be done on days when the rail reaches the NT by natural Heating and the NT is likely to remain constant within ± 3 oC through the entire duration of the forming operation.  If these conditions are not obtained, the operations shall be suspended.

In a temporary section (see paragraph IX. of the item 6A Construction of line), the 36 m long central zones are defined as central stretches (CS).

The CWR is formed by welding two contiguous temporary semi-sections, through the following operations:

I. disassembling the fastenings on all sleepers, except in the CS zones of the contiguous temporary semi-sections

II. disassembling the temporary joint between the two temporary semi-sections,

III. lifting the rail by means of stakes, starting from the joint towards the CS and inserting every 9 m expansion rollers into the rail seats, after removing the polyethylene pads; the expansion rollers, at least 20 mm in diameter, shall be positioned with their axles perpendicularly to the rail,

IV. jarring the rail with wooden mallet blows to facilitate its expansion and the removal of any hindrances to thermal expansion,

V. cutting thin slices off the rail ends to allow the free expansion of the temporary semi-section; this is necessary when the forming of the latter was done at temperatures below the NT. In the event of the temporary semi-sections having been formed at temperatures higher than the NT, a makeup rail shall be inserted to fill the gap due to thermal contraction. The length of the makeup rail shall be not less than 3 m.  The makeup rail shall be welded to either of the temporary sections ends,

VI. having reached the NT within ± 3 oC, forming the welded gaps, forming the weld gaps, quickly removing the expansion roller (starting from the CS), reinstalling the previously removed polyethylene pads, 

VII. assembling the fastenings, starting to the joint towards the CS, of the first 40 sleepers and next of one sleeper every three,

VIII. welding the joint,

IX. during the welding, completing the assembling of the fastenings,

X. immediately on completion of the casting of the thermic weld, disassembling the fastenings of 46 sleepers astraddle the joint in order to allow the thermal contraction of the weld on a rail length of at least 12 m on each side,

XI. after one hour, assembling the fastenings disassembled in step X.

Rail pulling 

When it proves impossible to form the CWR by natural heating, the use of rail tensor may be required.

The tensors shall be designed to permit the execution of thermic welds and be able of producing a 60 t pull without damaging the rails. 

Stress settling and CWR forming shall not be allowed to be done at temperatures under + 10 oC.

When rail pulling is used, the following operations shall be carried out, after applying the rail thermometers to the rails:

1. same as per point I.

2. same as per point II.

3. same as per point III.

4. same as per point IV.

5. affixing a reference mark on the rail foot on the ends of the two temporary semi-sections, recording the rail temperature, calculating the elongation to be produced in the two temporary semi-sections, multiplying 0,000012 by the length of the two temporary semi-sections and by the difference between the NT and the  temperature recorded on the rail,

6. applying the turnbuckles and pulling the rails till the calculated elongation  is achieved, as checked by reference marks, jarring the rails by wood mallet blows to facilitate elongation and remove any interferences therewith,

7. cutting thin slices off the rails ends to allow elongation,

8. when the calculated elongation is reached, quickly removing the expansion rollers starting from the CS and reassembling the rubber pads,

9. assembling the fastenings, starting from the joint towards the CS,

10. welding the joint, continuing to pull the rail till 3 minutes after the casting of the thermic weld to compensate for the tension stress of weld contraction during weld solidification,

11. loosening and removing the turnbuckles 10 minutes after the casting of the weld,

12. disassembling and immediately reassembling the fastenings of 46 sleepers astraddle  the weld

3.3 Methodology for beam substitution and rehabilitation of bridges

Beam substitution

In the present case there are only 5 small bridges to be repaired and the Lot 3.4 is supposed to be given to a construction contractor on the basis of a design and build contract. Thus the construction contractor is responsible for the technique to be adopted for the beam substitution.

The following should be, therefore, considered as a suggestion and should take into consideration that involves a small number of beams to be substituted (only 5 bridges) vis-à-vis a large number of machines.

Methodology for beam substitution should be that used in CIS here below shortly described.

Drawing L.3.4–1 in the attached Tender Documents of Lot 3.4 (Annex D) describes the methodology for substitution of beams of a three spans bridge.

In such case the operation considers two stages:

· I stage – replacement of the first two spans

· II stage – replacement of the third span

For bridges of two spans (which is the most common case along the line), the operation should be limited to the first stage.

Works to be carried out requires a special standard train made of two diesel loco at the ends, a platform wagon for beams, a crane (EDK-1000) including a platform wagon for the boom on rest/transport, a gondola wagon for ballast.

Stage I

Works to be carried out requires a windows of 8 hour and 20 minutes:

1. Closure of the line and work train leaving the station full loaded;

2. The train reaches the bridge;

3. The crane boom is freed and the train is divided into two parts positioned each one on the two different approaches to the bridge;

4. Ballast, sleepers and rails are removed from the two spans to be substituted near to the crane;

5. The crane removes the old beams from the nearest span, put them on the temporary site aside, replace the old beams with the new-ones;

6. The crane performs the same operation for the central span;

7. Ballast, sleepers and rails are replaced;

8. Old frames are collected and loaded on the train;

9. Loco N° 2 push platform for crane boom and gondola to form again an unique train;

10. Crane boom is fixed in the rest/transport position;

11. The train reaches a station;

12. Line is open to the traffic.

Stage II

Works to be carried out requires a windows of 5 hour and 30 minutes, operations are basically the same but only beams of one span are substituted. This stage is evidently not necessary for bridges of two spans or less.

The substitution of the beams should be operated before welding the rails in long bars.

Provision of beams and relevant devices are included. All of them have to comply with the standard design of Lengiprotransmost No 557, 1969 (see Figure 3.3.1 - 1).

Figure 3.3.1 - 1


[image: image25.wmf]Span

bridge floor

ballast

walkway slab

span beam

metallic console

walkway slab

The basic parameters on one span

overall 

length

effective 

span Lp, 

m

Building 

height from 

a sole of a 

rail up to 

pad stone

m

Mark of 

concrete

Volume of concrete

, m

3

Weight of armature,

 ton

Weight of 

one block 

with 

isolation,

 

ton

6.0

5.4

V-25

9.7

0.4

10.3

0.57

1.59

2.16

1.02

14.1

of the 

beam

s

Of the 

walkway 

slab

Total

A I

A II

Total

Class of 

the 

armature

A I, kg

Weight

ton

Volume 

of 

concrete, 

m

Mark of 

concrete

3.0

8.5

0.145

0.058

V-25

P-2

3

C

oncrete

Mark of 

element

The basic parameters on one 

walkway slab

Class of 

the 

armature

A II, kg

A

rmature steel

The basic sizes of 

elements,

cm

173

 

x

 

54

 

x

 

15

208 

x

 

54

 

x

 

15

P-5

V-25

0.07

0.175

10

3.7

780

4180

1300

1300

450

150

780

20

540

50

440

50

40

100

70

70

400

140


Waterproofing of ballast plates

Life time of reinforced concrete bridge superstructures in a great extent depends on waterproofing condition and fast water diversion from ballast plate and other surfaces of bridge superstructures.

Structure of surface waterproofing consists of preparatory isolating and protective layers (see Figure 3.3.1 - 2).

Figure 3.3.1 - 2


[image: image26.wmf]3

5

5

150

3

640

15

20

d=146

7

8

9

11

10

6

2

1

5

3

4

a)

b)

c)

d)

e)

i=0.033

i=0.033

Details of a waterproofing

(the sizes in mm)

a - design of a waterproofing;

b - waterproofing of the block of a span;

c - waterproofing at an external side;

d - waterproofing at an internal side;

e - 

drain-pipe

     

1 - a blanket;

     

2 - a metal grid;

     

3 - bitumen mastic;

     

4 - fiber glass fabric etc.

     

5 - a first coat bitumen it is delicious;

     

6 - concrete of waste prisms;

     

7 - a pipe;

     

8 - a bell-shaped pipe;

     

9 - clamping a glass;

     

10 - a cover;

     

11 - the bell, is filled bitumen (or on

           

epoxy

) mastic.

250

250

120

30

5

4

3

2

1

1 - preparatory layer

2 - 

w

aterproofing;

3 - 

b

lanket;

4 - 

s

teel sheet 

-

 =4 - 6 mm;

5 -

 t

he rod d=12

mm

, l=150 mm.

Overlapping of deformation seams

d=134

d=144

150


Bearings substitution

During replacement of the bridge superstructures the replacement of defective bearings is envisaged. 

It is allowed to install the reinforced concrete bridge superstructures with the length of 6 m on welded tangential bearings with the height of 20 cm (see Figure 3.3.1 - 3).

Figure 3.3.1 - 3

[image: image27.wmf]T1-A

T1-S

Quantity of 

bearings on 

the span

Lump of 

bearings on 

the span

Weight of one bearing 

sheet

 kg

Distance 

between 

anchors 

along an 

axis of the 

bridge

Sizes of the bottom 

bearing sheet

109

End 

reaction to 

the one 

carriage

ton

25

Design 

move

-

m

ent

mm

The basic parameters on one span

Height of 

the 

carriage 

mm

200

430

310

300

164

8

1316

Along an 

axis of

 the 

bridge

Across an 

axis of 

the 

bridge

actuated

 

bearing

stationary

 

bearing

h



[image: image28.wmf]T1-A

T1-S

Quantity of 

bearings on 

the span

Lump of 

bearings on 

the span

Weight of one bearing 

sheet

 kg

Distance 

between 

anchors 

along an 

axis of the 

bridge

Sizes of the bottom 

bearing sheet

109

End 

reaction to 

the one 

carriage

ton

25

Design 

move

-

m

ent

mm

The basic parameters on one span

Height of 

the 

carriage 

mm

200

430

310

300

164

8

1316

Along an 

axis of

 the 

bridge

Across an 

axis of 

the 

bridge

actuated

 

bearing

stationary

 

bearing

h


Repair of bridge piers

According to survey data reinforced concrete bridge structures have the following damages: cracks in the concrete, corrosion of armoring, leaching of concrete, separation of protective layer.

The following works are envisaged: cleaning from dust, dirt, leaching of concrete with rehabilitation of protective layer, trimming of cracks up to 0.15 mm with “polymer compound”, injection of cracks more than 0.15 mm with epoxy resin, improvement of waterproofing and water diversion defects on bridge superstructures is carried out from overhead rail package with the length of 5 m.

Overhaul works of piers are carried out from outside scaffoldings

Repair of abutment 

Works implemented into “window” include:

· Cutting out of defective layer with the thickness of 4 cm on bearing blocks;

· Sealing up of chips with the monolithic concrete B 25;

· Dismantling of reinforced concrete laying, destroyed cordon stones;

· Installation of new reinforced concrete bearing blocks PB-1, PB-2 

· Installation of new cordon blocks CB-1 and cabinet type blocks 

Works implemented “under the train traffic conditions” include:

· Sealing up of chips with the thickness of 2 cm in reinforced concrete bearing blocks;

· Cement floating of abutment surface;

· Protective layer rehabilitation with cement;

· Sealing up the cracks.

3.4 Construction of a new avalanche shed

The avalanche sheds are built as follows.

The structure of the existing avalanche sheds is composed by irregular concrete blocks on the mountain side and, on the other side, by pillars made by regular concrete blocks fixed in a hole in the foundation having the same shape section of the pillar.

The basic structural element is the “concrete block”, a pre-cast concrete unity with low content of cement, used to fill up the gravity walls and with a major content of cement and in more regular shapes as active structural element, if necessary integrated with epossyc resins or structural expansion mortar.

On the mountain side, the concrete block is used both for gravity walls and for support zone of roof beams. On the other side of the gallery is used for assembling pillars and as beams supporting the roof (edge beams). 

The link between pillars and foundations is implemented with the so-called “glass system”, without armature, while the edge beams simply lay on the top of pillars.
The result is a structure based on slender isolated elements, as the pillars are, that offers a poor resistance against the horizontal stresses transmitted by earthquakes.

The following measures are necessary to improve the existing structures:

· Connecting the plinth with reinforced concrete foundation beams and doing the same thing at the head of the pillars; that could be sufficient to increase the stiffness of the structure in acceptable measure.

· Performing an accurate inspection of the critical area in order to identify the must unstable rock blocks and then proceeding to their controlled removal.

· In addition to this clean up of the slopes, rock fall protection systems (like drapery wire mesh or rock-fall protection barrier) could be applied in the most endangered sections of the area.

· The cover of the structures has to be attentively controlled from time to time to ascertain its impermeability as well as the canalization for sending away the rain water.

The implementation of the 500 meters missing for the completion of the second avalanche shed has to be designed taking in due account all the structural consideration above mentioned. Before the beginning of the works, the measures above recommended are to be implemented to reduce the risk for the workers attending to the building activities.

4. Purchase of machines (Lot 3.1)

4.1 Description and bill of quantity

Number and type of machine to be purchased have decided according the rationale that Kyrgyz will be performing all activities (but more serious works) and considering the fleet of machine they own already.

Because of the involvement of a minor number of machines, the Consultant suggests to use the Methodology 1 (European) for track construction. Thus purchase of machines has considered such methodology.

The following Table 3.1-1 shows the related bill of quantities.

Table 4.1-1 – Bill of Quantities

	Item Description
	Code
	Q-ty
	Unit
	Note

	Tamping Machine
	24-A1
	1
	unit
	including accessories and spare parts

	Profiler Machine
	24-A2
	1
	unit
	including accessories and spare parts

	Gantry Crane
	24-A3
	2
	unit
	including accessories and spare parts

	Positioner
	24-A4
	1
	unit
	including accessories and spare parts

	Loader for ballast quarry operation
	24-A5
	2
	unit
	including accessories and spare parts

	Welding machine
	24-A6
	1
	unit
	including accessories and spare parts


4.2 Costs estimates

The capital cost has been estimated starting from the bill of quantities above mentioned (Table 4.1-1) which details the number of every specific equipment to be purchased.

In the subsequent stage, these quantities have been associated to the correspondent unit rate in order to produce the final estimation of the global capital costs of the complete lot. The unit rates reflect market prices and conditions prevailing at the beginning of 2005 and also include costs for transportation of the equipment as well as costs for accessories and spare parts and eventual costs for adaptation to the wider gauge.

Finally, as the equipment is normally exempt form taxes and duties on imported goods especially vis-à-vis funds from IFIs, all taxes have been omitted in the study.

The final cost for the whole Lot is around 8.4 millions of US$.

5. Purchase of permanent way materials (Lot 3.2)

5.1 Description and bill of quantity

Due to the fact that Kyrgyz Railway will be performing maintenance activities, Lot 3.2 has been limited to the purchase of materials.

Quantity of permanent way material has been determined by a careful analysis of the need of rehabilitation and of the volumes involved.

As far as item 2B is concerned, the amount of sleepers considers that the sleeper factory will be operative only after 12 months and meanwhile the Kyrgyz Railway will start the extraordinary maintenance.

As for item 4B, the capacity production of the quarry is limited actually to the strict necessary for the routine maintenance. Such production will be increased by the machines to be purchased but an additional input (in terms of ballast) is necessary meanwhile in order to start extraordinary maintenance immediately. Such amount has been calculated under the assumption it will take one year before getting the machines and so modifying the production levels.

To start with extraordinary maintenance immediately is the advice of the Consultant. Of course if Kyrgyz Railways decide not to follow such suggestion it is advisable to reduce items 1B and 4B amount according to the objective needs. This will have a repercussion on the Lot cost.

The following Table 5.1-1 shows the related bill of quantities.

Table 5.1-1 – Bill of Quantities

	Code
	Description
	Unit
	Quantity
	NOTES

	1B
	P65 rails
	t
	6.200
	Corresponding to 48 km of single track line 

	2B
	Concrete sleepers
	unit
	100.000
	100,000 sleepers corresponding
 to 55 km

	3B
	Fastenings for concrete sleepers 
	pairs
	100.000
	

	4B
	Ballast for rehabilitated sections
	m³
	40.000
	Corresponding to 22 km of single track line 

	9B
	Switch crossing
	unit
	100
	50 for R65 and 50 for R50

	10B
	Switch blades
	pairs
	100
	50 for R65 and 50 for R50

	12B
	Rail Joints
	each
	4.100
	

	13B
	Insulated rail joints
	each
	1.500
	


5.2 Costs estimates

The capital cost has been estimated starting from the bill of quantities above mentioned (Table 5.1-1) which details the number of every specific equipment to be purchased.

In the subsequent stage, these quantities have been associated to the correspondent unit rate (Table 5.2-1) in order to produce the final estimation of the global capital costs of the complete lot. The unit rates reflect market prices and conditions prevailing at the beginning of 2005 and do not include costs for transportation which has been included at the end at an average rate of 6% of the lot cost.

Finally, the figure doesn’t consider taxes and duties on imported goods especially vis-à-vis funds from IFIs. Thus all taxes have been omitted in the study.

Table 5.2-1 Unit Costs

	Code
	Description
	Unit
	Rate (US$)
	NOTES

	1B
	P65 rails
	t
	450,00
	

	2B
	Concrete sleepers
	unit
	30,00
	

	3B
	Fastenings for concrete sleepers 
	pairs
	20,00
	

	4B
	Ballast for rehabilitated sections
	m³
	6,00
	

	9B
	Switch crossing
	unit
	4.000,00
	50 for R65 and 50 for R50

	10B
	Switch blades
	pairs
	15.600,00
	50 for R65 and 50 for R50

	12B
	Rail Joints
	each
	25,00
	

	13B
	Insulated rail joints
	each
	34,00
	


The final cost for the whole Lot is around 10.8 millions of US$.

6. Purchase of a sleeper factory (Lot 3.3)

6.1 Description

Purpose of the tender is the supply of a sleeper factory for the Kyrgyz Railways according to the following requirements:

· the plant is to be for an average production capacity of 100.000 sleepers per year and so assuming 8 hours working shift, one working shift per day and 250 working days per years a production of a minimum 400 sleepers per working days is required;

· the plant is to be easily upgraded for the a second working shift;

· the plant has to produce sleepers 1520 mm gauge, 2700 mm length and equipped with KB fastening type, according to Standard GOST 10629;

· the plant has to produce pre-stressed concrete sleeper reinforced with improved adhesion wires. 

· the manufacturing plant has to be “mobile” and so all equipment should be designed to be easily taken apart for transportation and installation at a new factory site;

· the manufacturing plant has to be equipped with safety protection in all the areas where there are machines in motion;

· different phases of the manufacturing are to be executed with computerised quality control keeping records of each critical operation;

· all components have to be first class standard certified;

· the plants should ensure the full production capacity within 4 months from the start-up.

The following ancillary equipments are not included in the request for quotation:

a) Main electric board (machines supply)

b) Safety devices 

c) Laboratory testing equipment

d) Self-stressing moulds (characteristics and number are part of the proposal)

e) Auto threading machine for steel wire preparation

f) Auto end void grouting machine to grout the holes at the ends of sleepers

g) Concrete batching plant, including installation

h) Steam generator 400 steam/hour

i) Air compressor 25 kW

j) Fork lift truck 10 tons capacity

The Consultant’s advice is that such ancillary equipments are not only for facilitating the production but also for improving the quality of the products (sleepers). If Kyrgyz Railways have not such equipment, it is advisable to possibly integrate some of those equipments in the sleeper factory supply. This, of course, will increase costs.

6.2 Cost estimate

The cost of the sleeper factory has been estimated by a market investigation.

The cost of the lot reflecting market prices and conditions prevailing at the beginning of 2005, including costs for transportation and without taxes is of about 2.0 millions of US$.The global cost for the ancillary equipment is of about 1.0 million of US$ but it has not been included in the lot and in the relative requirements.

7. Detailed Design of Civil works (Lot 3.4)

7.1 Description and bill of quantities

Works included in this lot are:

· Substitution of damaged beams in 5 bridges;

· Maintenance of piers and abutments in 5 bridges;

· New construction of an avalanche shed;

· Quarry rehabilitation (near Djil Aryk).

Therefore description of the present situation and detailed design have been limited to those aspects included in the Lot 3.4.

It is worth mentioning that the adopted tender documents for “design and build” gives to the construction contractor the full responsibility of developing the executive design following the so called “employer’s requirements”.

The detailed design performed by the Consultant is due just for formulating the employer’s requirement and not for other elaborations.

On the contrary the construction contractor is the sole responsible of the executive design and of the works implementation. In such circumstances, the detailed design made by the consultant has to be seen as a base/advise which doesn’t prevent the construction contractor to propose other works methodology and formulate their financial proposal accordingly.

The following Table 7.1-1 shows the bill of quantity for the related works.

Table 7.1-1 – Bill of quantities
	Code
	Description
	Unit
	Quantity
	Notes

	22A
	Renewal of bridges beams
	each
	18,00
	4 bridges are 2X6 m span; 1 bridge is 1X6m span

	23A
	Maintenance of piers and abutments
	each
	14,00
	

	26A
	Construction of avalanche shed
	m
	500
	It includes measures to improve the existing sections

	27A
	Quarry rehabilitation
	unit
	1
	

	19B
	Bridges beams
	each
	18,00
	4 bridges are 2X6 m span; 1 bridge is 1X6m span


7.2 Costs estimates

7.2.1 Unit costs 

The analysis was aimed at detailing all the cost items, including foreign and national expenditures for materials, foreign and national cost for man-power, cost of the machines and expenditures for taxes, duties and Contractor and Client general expenditures.

For the Infrastructure, the construction cost is subdivided into the following types of work and expenditures in accordance with the structure of capital investments and the planned schedule of activities of constructing-and-mounting companies (Contractors):
· Materials;

· Construction works;
· Miscellaneous expenditures of a contractor;
· Miscellaneous expenditures of a customer.
A Contractor includes in the above cost both direct and concomitant expenditures (factor costs, miscellaneous expenditures, profit, and also funds for payment of taxes, duties and other obligatory payments).
Direct expenditures (including miscellaneous ones) are the expenditures of a contractor to construct a requested object that is labour and material resources, etc. 
When calculating a construction cost, the following types of work and expenditures are considered:
1. Materials cost – cost of the necessary building materials, divided in national and foreign costs, according to the production Country;

2. Manpower Construction works – works on construction of buildings, different types of structures, finishing works, installation of external and internal engineering networks, installation of foundation and supporting structures for equipment, preparation a site for construction , etc.;
3. Manpower Mounting works - assembly and installation of devices at the place of their permanent operation (including inspection and individual testing of all kinds of equipment, electric installations, devices, computer engineering, connection of the equipment to engineering networks and other works);
4. Miscellaneous expenditures are the rest of expenditures not included in the factor costs for construction-and-mounting works, including:
· Other industrial expenditures defined for a construction project (a contractor’s expenditures); 
· For organisation of construction works (overhead expenses);
· For construction of temporary buildings;
· For performing works in winter time;
· For long service bonus;
· For additional leave of workers;
· Travelling expenses;
· For transportation of workers up to the building object;
· For relocation of construction-and-mounting organisations;
· For a mobile method of work performance;
· Insurance of construction risks;
· Obligatory payments (taxes), duties in conformity with the legislation of the Republic of Kyrgyzstan
· Unforeseen costs and other expenditures for construction of objects.
Besides, the construction cost includes other expenditures of a customer during the construction:
· Allotment of a piece of land for construction of an object and external engineering structures;
· Fixing of points and signs;
· Demolition of structures;
· Bonus for timely and prescheduled commissioning of objects;
· Insurance of building risks;
· For banking services;
· Loan interests;
· Maintenance of a customer’s facilities;
· Training of operational staff;
· Design and survey works;
· Survey works;
· Expertise of the design documentation;
· Profit necessary to cover the expenditures of a customer;
· Unforeseen costs.
The cost of the above mentioned expenditures is defined through calculations or through actual expenses of a customer and a contractor.
In the conditions of the market economy being developed in Kyrgyzstan, the prioritized importance is attached to the method of calculating a construction cost based on the cost of resources. This method of defining a construction cost is a method of calculating expenditures in current prices or forecast prices and tariffs to be incurred during a project implementation. 
A construction cost in current prices is defined on the basis of resource estimates developed through the above mentioned resource method with the use of information on actual prices for resources.

The factor cost is determined based on the allocated resources in current prices by types of expenditures:
a) wages including charges on social insurance;
b) maintenance cost of machines and mechanisms;
c) cost of building materials, items and structures including their transportation.
When calculating a construction cost, the level of current prices is taken on the basis of:
· wages – average statistical wage of construction workers as per the data of the State Committee on Forecast and Statistics;
· maintenance of machines and mechanisms – as per similar objects or special calculations;
· materials, items, structures, equipment - proceeding from the price level at the local and foreign markets, on the basis of wholesale prices of manufacturing factories, prices at stock exchanges and fairs of building materials.
7.2.2 Cost calculation flow

The following Table 7.2.2-1 resumes the main factors for calculation of the total cost amounts. 
Table 7.2.2 – 1 Main factors for calculation of total cost amounts

	Rehabilitation works for Kazakh border - Bishkek - Balykchi section

	"General data for project cost estimation"

	Transport expenditures for materials
	
	6
	%

	Transport expenditures for constructions
	
	6
	%

	Risk coefficient
	
	1.15
	coeff.

	Other expenses and cost of contractor
	
	15
	%


Other expenses and costs of the contractor include:

· profit;

· administrative costs of the company;

· fix costs for the company;

· other general expenses.

In addition 20% taxes should be considered.

The following table resumes the cost calculation flow.

Table 7.2.2 - 2 Cost calculation flow
	Rehabilitation works for Kazakh border - Bishkek - Balykchi section

	 "Project cost calculation flow"

	Item 
	Article of expenses
	Calculation

	
	
	method

	A
	Cost of construction + 6% transport 
	A

	B
	Other expenses and costs of the contractor
	B=15%A

	C
	Total cost of construction and contractor expenses 
	C=A+B

	D
	tax 20% 
	D=20%C

	E
	Total cost of construction and contractor expenses with taxes
	E=C+D

	F
	Risk coefficient defined on basis of forecasted index of construction price growth for the following year
	F=15%E

	T
	Lot cost
	T=E+F


The following table 7.2.2-3 resumes the result of cost analysis for the Lot 3.4 and Civil Works. It has been developed according to the detailed bill of quantities, the unit cost and the rationale above provided.

Table 7.2.2-3 Lot cost analysis
	Rehabilitation works for Kazakh Border – Bishkek – Balylchi section

	 "Lot 3.4 Civil Works"

	Item number
	Article of expenses
	Cost

	
	
	($)

	A
	Cost of construction + 6% transport
	5.000.000,00

	B
	Other expenses and costs of the contractor
	750.000,00

	C
	Total cost of construction and contractor expenses 
	5.750.000,00

	D
	tax  20%  
	1.150.000,00

	E
	Total cost of construction and contractor expenses with taxes
	6.900.000,00

	F
	Risk coefficient defined on basis of forecasted index of construction price growth for the following year
	1.035.000,00

	T
	Lot cost
	7.935.000,00


8. Implementation schedule

The following Table 8 - 1 shows the implementation plan for the works envisaged for the four Lots and for the activities to be carried out by the Kyrgyz Railways.

All the scheduled activities will be completed in 60 months.
Table 8.1 Implementation programme


[image: image29.wmf]Lot 3.1. Purchase of machines

Approval of financement

Final tender document preparation

Orders of machines

Production and delivery of machines

Lot 3.2. Purchase of materials

Approval of financement

Asking and reciving offers

Asking and receiving offers  

Orders of materials

Production and delivery of materials

Lot 3.3. Purchase of a sleeper factory

Approval of financement

Final tender document preparation

Asking and receiving offers  

Production of sleeper factory

Installation - tests

Final tender document preparation

7

11

15

14

12

13

10

9

8

6

5

4

2

3

1

page 1/2

ACTIVITY/months



[image: image30.wmf]22

Execution of works - acceptance tests 

(  ) The detailed implementation programme is depending on availability of resources, but it is assumed to be completed within 60 months from the approval of funding.

Rehabilitation of raillway line (  )

ACTIVITIES TO BE DONE BY KYRGYZ RAILWAYS

30

26

Execution of works - acceptance tests 

Ordering of spare parts

Installation and acceptance tests 

Production and handing over of spare parts

29

28

QUARRY

27

Ordering materials 

Mobilisation of worksite

Production and handing over of materials

25

24

23

BRIDGES

page 2/2

Tendering and signature of contract for civil works 

18

Mobilisation of worksite

Ordering materials 

Production and handing over of materials

AVALANCHE SHED

21

20

19

Lot 3.4. Civil works

Approval of financement

Final tender document preparation

17

16

ACTIVITY/months


9. Tender Documents

9.1 Introduction

Purpose of this activity is “to prepare contract packages for international competitive bidding, international shopping, and direct purchase in accordance with standards development bank procedures”.

The scope of each package depends on the recommended solutions in the Feasibility Studies (FS). The following detailed design of the recommended improvement has given the input to the tender documents preparation.

Besides the technical recommended solutions, the procurement activities are deeply affected by standard development bank procedures. Despite a common philosophy, each bank normally has its own Guidelines for Procurement or a standard document to be adapted time by time.

On the other hands, the Consultant can’t produce tender documents taking into consideration all factors deriving form all the possible combination among: several feasible packages and four (maybe more) standard documents (EBRD, ADB, IDB, World Bank, national).

All the above results in the following:

· each package has been prepared in accordance with requirements of the Guidelines of possible financing banks, which assure International Competitive Bidding;

· the Consultant can produce only a “draft tender document” since several details (for instance (i) tender Identification Number, (ii) Deadline for submission of the Tender, (iii) time, date and place of tender opening, (iv) date and location of pre-tender or site meeting, (v) Employer’s address, etc.) are not known at the moment and will be known in the time being up to end of the project;

· several details are susceptible to be changed before the date of the tender publication.

9.2 The adopted philosophy for procurement

The Consultant has developed the philosophy for a successful procurement of the Package taking into consideration the following basic criteria.

The Standard Bidding Documents of Asian Development Bank (ADB) have been adopted.

It is noted that the Standard Bidding Documents adopted from various banks such as WB, EBRD, IDB, ADB, etc. slightly differs one each other.

In fact the above said banks have adopted since many years a policy of homogenization of the Tender Documents.

Such approach of using international standards leaves open the possibility of adopting guidelines of procurement of Institutions other than ADB.

Basically the legal relationships between the Borrower and the Bank are governed by the Loan Agreement. However, in the present circumstance, the procurement procedures are undertaken before signing the related Bank loan. 

The rights and obligations of the Borrower and the providers of goods and works for the project are governed by the bidding documents, and by the contracts signed by the Borrower with the providers of goods and works.

In fact, for major contracts involving the procurement of advanced technological equipment it is common practice to develop the procurement procedures through an International Competitive Bidding (ICB).

The objective of ICB is to provide all eligible prospective bidders with timely and adequate notification of a Borrower’s requirements and an equal opportunity to bid for the required goods and works.

The bidding documents shall clearly state the type of contract to be entered into and contain the proposed contract provisions appropriate therefore. The most common types of contracts provide for payments on the basis of unit prices or a lump sum.

For Lot 3.1 Purchase of machine and Lot 3.2 Purchase of materials, the ADB Standard Tender Documents (STD) for Procurement of Goods have been taken as reference while for Lot 3.3 Purchase of a sleeper factory and Lot 3.4 Civil Works, the ADB Standard Bidding Documents (SBD) for Design-Build and Turnkey have been taken as reference.

A. STD for Procurement of Goods. 

The ADB’s STD for Procurement of Goods are used for contract where the supply of goods and material prevails on the installation works and other related services. 

The Single-Stage: One-Envelope bidding procedure is the main bidding procedure used for most of the procurement financed by the ADB. In the Single-Stage: One-Envelope bidding procedure, Bidders submit Bids in one envelope containing both the Price Proposal and the Technical Proposal. The envelopes are opened in public at the date and time advised in the Bidding Document. The Bids are evaluated and the Contract is awarded to the Bidder whose Bid has been determined to be the lowest evaluated substantially responsive Bid.

In accordance with ADB established procedures, prequalification of bidders is required for procurement contract related to expensive and technically complex items to ensure that only experienced and financially capable firms will submit bids. 

Therefore a combination of :

· ADB’s SPD for Prequalification, and

· ADB  SBD for Procurement of Goods with Single Stage – One Envelope procedure

The main data provided by the Consultant are on the results of the Detailed Design, and are namely:

· For the SPD for Prequalification:

· Short description of the project

· Major contract components

· Estimated quantities of major components

· Contract implementation period

· For the SBD for Procurement of Goods with Single Stage – One Envelope procedure:

· List of goods and related services

· Technical specifications of goods and related services

· Drawings

B. Standard Bidding Documents (SBD) for Design-Build and Turn Key Contract with Single Stage bidding procedure. 

There are no universally-accepted definitions of the terms "design-build" and “turnkey", except that both involve the Contractor's total liability for design. For the Employer, such single-point responsibility may be advantageous, but the benefits maybe offset by having less control over the design process and more difficulty in imposing varied requirements.

Under the usual arrangements for a design-build contract, the Contractor is responsible for the design and provision, in accordance with the Employer's requirements, of works which may include any combination of engineering (including civil, mechanical, electrical, etc) and building works; and interim payments are made as construction proceeds. 

The Conditions are also intended for use on turnkey contracts, under which the Employer's requirements usually include provision of a fully equipped facility, ready for operation (at the turn of the "key"). Turnkey contracts typically include design, construction, fixtures, fittings and equipment, the scope of which would be defined.”

Turnkey contracts involve the contractor's single responsibility for design, manufacture, delivery, installation, testing, commissioning, training, etc.

In the Single Stage bidding procedure the bidders submit one envelope containing the price proposal and the technical proposal. The envelope is opened in public and the total amount of each bid and any alternative bid and other relevant details are read out and recorded. The bid is evaluated the award of contract is made to the lowest evaluated substantially responsive bidder. The Single Stage bidding procedure is normally utilized for contracts where the plant to be designed and build is very well defined or where the civil works content is very high such as for roads, pipelines and power transmission line projects where there is not likely to be problems in the evaluation of alternative proposals for machinery or equipment. 

In accordance with ADB established procedures, prequalification of bidders is required for civil works, turnkey contracts and contracts for the fabrication of expensive and technically complex items to ensure that only experienced and financially capable firms will submit bids. 

ADB's Standard Procurement Documents (SPD) for the Prequalification of bidders are based on Master Procurement Documents prepared jointly by multilateral development banks and other public international financing institutions. 

The Tender Documents are constituted by a combination of:

· ADB’s SPD for Prequalification, and

· ADB  SBD for Design-Build and Turn Key Contracts with Single Stage procedure.

The main data provided by the Consultant are on the results of the Feasibility Studies, and are namely:

· For the SPD for Prequalification:

· Short description of the project

· Major contract components

· Estimated quantities of major components

· Contract implementation period

· For the SBD for Design-Build and Turn Key Contracts with Single Stage procedure:

· Employer’s Requirements. Care must be taken when drafting the Employer’s Requirements to ensure that the requirements are not restrictive. In the specification of standards of goods, materials and workmanship recognized international standards should be used as much as possible. Where other particular standards are specified, whether national standards of the Borrower’s country or other standards, it should be state that goods, materials and workmanship meeting other authoritative standards and which promise to ensure equal or higher quality than the standards specified, will also be acceptable. Where a brand name of a product is specified it should always be qualified with the terms or equivalent. In addition to stating the requirements of the completed Works clearly the Employer Requirements Section should also include matters related to the execution of the Works to enable the bidders to gauge the extent of responsibility and to price the bid accordingly.

10. Conclusions

Following the positive results of the Feasibility Study, the Consultant has prepared the detailed design necessary for the development of the related tender documents 

Except for main civil works (bridges and avalanche shed), the rehabilitation will be performed directly by the Kyrgyz Railways using the internal personnel.

Such proposed option represents the low cost alternative, mainly consisting in provision of PW materials, machines and plants that would permit to face the most urgent necessities of the line, as well as in building the indispensable structures to guarantee the line protection from land-slides. It would allow the acceleration of the capital maintenance of the remaining network putting at disposal recovered rails and machines to implement works with Kyrgyz railways personnel.

Since the proposed option has been validated in meetings with high representatives of the Kyrgyz Railways, the Consultant has consequently undertaken the Detailed Design and the Tender Documents preparation.

The option considers in particular the categories in which the whole rehabilitation works can be divided to be:

a. Civil works concerning earthworks;

b. Permanent way replacing works

c. Existing permanent way rail welding and tension regulation;

d. Re-alignment, leveling and ballast cleaning on the existing sections;

e. Civil works concerning structures (basically bridges and avalanche shed).

The activities concerning civil works for structures (bridges and avalanche shed) are to be developed by a Contractor on the basis of a design and build contract.

All other works will be performed directly by the Kyrgyz Railways using internal personnel following the purchase of materials, machines and plants.

Therefore four lots have been considered:

· Lot 3.1 – Purchase of machines

· Lot 3.2 – Purchase of Permanent Way materials

· Lot 3.3 – Purchase of a sleeper factory

· Lot 3.4 – Civil works

Lot 3.4 also includes the rehabilitation of the ballast quarry near Djil Aryk in order to reach a proper level of efficiency and increase the production needed for the rehabilitation of the railway track.

In all cases the tender should be lunched using international standards (ADB standards) but the work performed, leaves open the possibility of adopting guidelines of procurement of other bodies. Thus the approach doesn’t prevent the Beneficiary to implement the project using other guidelines (i.e. World Bank, EBRD, national, etc.) simply taking the core part of the tender document, namely the technical drawings and specifications, and embedding them into a different set of standards documents.

For Lot 3.1 and Lot 3.2, the ADB Standard Tender Documents (STD) for Procurement of Goods have been taken as reference while for Lot 3.3 and Lot 3.4, the ADB Standard Bidding Documents (SBD) for Design-Build and Turnkey have been taken as reference.

The Consultant has presented such documents in separate Annexes (Annex A, B, C and D) which can be straight used for the tender just including some basic additional information from the Beneficiary (i.e. employer’s name and address, representative of the employer, deadline for presentation, etc).

Finally, despite the positive results, it has to be pointed out that the project has been largely affected by the national Kyrgyz law covering “classified information”.

As already explained, this heritage of the former Soviet Union prevents the access to a large series of information to foreign people including those geographically referred such as detailed maps, locations of stations/bridges/structures and including train timetable, traffic details, etc.

It is worth mentioning that such constraints could have also counterproductive effects vis-à-vis design standards required by IFIs for releasing a loan. Thus other projects could be preferred just for being better presented: for instance such constraint didn’t’ allow the Consultant to produce plans and profiles and has required a working methodology more numerical/analytical so less intuitive.

Notwithstanding Kyrgyz Railways have always been observant of the rules, they have been also very constructive in supporting experts staff both in the site visits and in the technical discussion.
[image: image42.png]4
”ITALFERR



[image: image43.png]4
”ITALFERR



[image: image44.png]4
”ITALFERR



[image: image45.png]4
”ITALFERR





















































































The European Union’s Tacis TRACECA programme


for Armenia, Azerbaijan, Bulgaria, Georgia, Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, 


Turkmenistan, Ukraine, Uzbekistan 


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, 


Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 








The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 





The European Union’s Tacis TRACECA programme


for  Armenia, Azerbaijan, Bulgaria, Georgia,  Kazakhstan, Kyrgyzstan, Moldova, Romania, Tajikistan, Turkey, Turkmenistan, Ukraine, Uzbekistan 


























Published July 2005





This publication has been produced with the assistance of the European Union.


The contents of this publication is the sole responsibility of Italferr S.p.A. 


and can in no way be taken to reflect the views of the European Union.





� EMBED MSPhotoEd.3  ���


A project implemented by


Italferr S.p.A.





This project is funded by


the European Union





Review of Railways Rehabilitation in Central Asia





for Kazakhstan, Kyrgyzstan, Tajikistan and Uzbekistan








Module B – Detailed Design and Tender Documents of the rehabilitation measures for the Kazakh Border – Bishkek – Balykchi railway section (Kyrgyzstan) – DRAFT





July 2005










































[image: image46.png]4
”ITALFERR



[image: image47.png]4
”ITALFERR



[image: image48.png]4
”ITALFERR



[image: image49.wmf] 

[image: image50.png]


[image: image51.jpg]


_1171900256.dwg

_1184335767.dwg

_1184335994.dwg

_1184593119.dwg

_1184593220.dwg

_1184483806.dwg

_1184335937.dwg

_1172477868.dwg

_1176905381.dwg

_1172238217.dwg

_1170500010.dwg

_1171897469.dwg

_1171899142.dwg

_1171898298.dwg

_1171895279.dwg

_1162630734.bin

_1170484220.dwg

_1118147060.bin

_1099325645.bin

